## Sheet1
SerialNo | ProjectID | More | ProjectCode | LOC NUMBER | Purpose | Category | Sr. no. | LOC Ref. No. | Country | LOC amount (USD million) | Project | Project Cost for which PQ is being /was undertaken (USD mn) | Category | PQ documents published on | Last date for submission | Date of Contract Signing | Date of receipt of Contract Agreement & Contract Inclusion Form by Exim Bank | Date of Contract Inclusion by Exim Bank | Status
362 | 121 | 1 | GOILOC-246(P-1) | GOILOC-246 | Renovation/up-gradation of Bulawayo Thermal Power Plant | PQ process completed - Contract yet to be awarded |  | G-246 G-298 | Zimbabwe | 110 | Renovation/up-gradation of Bulawayo Thermal Power Plant | 87 | EPC | 2019-01-07 | 2019-03-14 |  | NA | NA | Pre-Qualified Companies List: i) Bharat Heavy Electricals Ltd [BHEL]. ii) ISGEC Heavy Engineering Ltd [ISGEC] Contract Award: Yet to be awarded. 1. ZPC has initiated the tendering process on 14.11.2019 and the last date for submission of the tender documents was 11.02.2020. The same has been extended till 11.04.2020.
363 | 122 | 1 | GOILOC-247(P-1) | GOILOC-247
364 | 123 | 1 | GOILOC-248(P-1) | GOILOC-248
365 | 124 | 1 | GOILOC-249(P-1) | GOILOC-249 | Procurement of Trucks for Bangladesh Road Transport Corporation [BRTC]
366 | 125 | 1 | GOILOC-249(P-2) | GOILOC-249 | Procurement of Double Decker and Single Decker AC & Non-AC Buses for Bangladesh Road Transport Corporation [BRTC]
367 | 126 | 1 | GOILOC-249(P-3) | GOILOC-249 | Procurement of equipment and machinery for Roads and Highwayss
368 | 127 | 1 | GOILOC-249(P-4) | GOILOC-249 | Improvement of Ashuganj River Port-Sarail-Dharkhar-Akhaura Land Port Road as 4-Lane National Highway
369 | 128 | 1 | GOILOC-249(P-5) | GOILOC-249 | Construction of Double Line Track in Khulna-Darsana Junction Section of Bangladesh Railway
370 | 129 | 1 | GOILOC-249(P-6) | GOILOC-249 | Construction of new carriage Workshop in Saidpur Railway Workshop including feasibility study
371 | 130 | 1 | GOILOC-249(P-7) | GOILOC-249 | Conversion of Meter Gauge Line to Dual Gauge Line in Parbatipur-Kawnia Section of Bangladesh Railway
372 | 131 | 1 | GOILOC-249(P-8) | GOILOC-249 | Barapukuria-Bogra-Kaliakoir 400 KV Line Project
373 | 132 | 1 | GOILOC-249(P-9) | GOILOC-249 | Establishment of Indian Economic Zones in Mongla, Bagerhat
374 | 133 | 1 | GOILOC-249(P-10) | GOILOC-249 | Upgradation of Infrastructure/ facilities in 49 Poly-technic Institutions in Bangladesh to create opportunities for additional enrolment of 1 Lakh Students
375 | 134 | 1 | GOILOC-249(P-11) | GOILOC-249 | Establishment of Jamalpur Medical College and Hospital, Jamalpur
376 | 135 | 1 | GOILOC-249(P-12) | GOILOC-249 | Bangabandhu Sheikh Mujib Shilpanagar project
377 | 136 | 1 | GOILOC-249(P-13) | GOILOC-249 | Establishment of Inland Container River Port at Ashuganj
378 | 137 | 1 | GOILOC-249(P-14) | GOILOC-249 | Establishment of 500-bedded Hospital & Ancillary Buildings in Jessore, Coxs Bazar, Pabna and Noakhali Medical Colleges
379 | 138 | 1 | GOILOC-250(P-1) | GOILOC-250
380 | 139 | 1 | GOILOC-251(P-1) | GOILOC-251 | Supply of machine for packing food item
381 | 140 | 1 | GOILOC-252(P-1) | GOILOC-252 | Transmission Line and Substation in Sierra Leone | PQ process completed - Contract yet to be awarded |  | G-252 | Sierra Leone | 78 | 225 KV/66 KV/ 33 KV double/single circuit transmission lines and associated substations | 67.67 | PMC | 2019-06-10 | 2019-07-10 |  | NA | NA | Four applications were received for which evaluation has been compleated and list has been shared to Govt. of Sierra Leone on September 13, 2019. Prequalified companies are: i. Power Grid Corporation of India Ltd. ii. Wapcos Ltd. iii. Virtuous Energy Pvt. Ltd. The RFP was issued on December 13, 2019 and the last date of submission is January 29, 2020. Govt. of Sierra Leone informed that only two prequalified companies i.e. Wapcos Ltd. and Virtuous Energy Pvt. Ltd. has submitted the bids. Bid evaluation report is awaited from GO-SLE.
382 | 141 | 1 | GOILOC-253(P-1) | GOILOC-253 | Project Trident [Construction of berthing jetty and Head Quarter building for National Coast Guard of Mauritius] | PQ process completed - Contract yet to be awarded |  | G-253 | Mauritius | 52.3 | Project Trident | 52.3 | CC | 2019-04-02 | 2019-05-24 |  | NA | NA | List of prequalified companies forwarded to GOM on 17.07.2019 for undertaking the tendering process are as under:- i. Afcons Infrastructure Ltd. ii. ITD Cementation Ltd. iii. Larsen & Toubro Ltd. iv. Navayuga Engineering Company Ltd. v. Simplex Infrastructure Ltd. Tender document was disseminated by RITES Ltd. on 23.10.2019 and last date for submission of bid was 21.01.2020. The Bids are now evaluated by RITES/GOM. Awaiting techninical bid evaluation report for vetting purpose.
383 | 142 | 1 | GOILOC-254(P-1) | GOILOC-254 | Construction and Execution of the works related to Rehabilitation and Improvement of water supply scheme in Zanzibar, Tanzania | PQ process completed - Contract yet to be awarded |  | G-254 | Tanzania | 92.18 | Construction and Execution of the works related to Rehabilitation and Improvement of water supply scheme in Zanzibar, Tanzania | 89.42 | EPC |  | 2019-01-10 |  | NA | NA | PQ document was published on Exim Bank's website on November 26, 2018. The last date for submission of PQ applicatons was extended to January 10, 2018. 15 applications were received and evaluated and 9 applicants have been pre-qualified. Pre-Qualified Companies List: 1. LARSEN & TOUBRO LIMITED 2.Laxmi Civil Engineering Services P Ltd 3. Afcons-Vijeta JV 4. Jayanti Super Construction P Ltd 5. SPML Infra Limited 6. MEIL 7. SMC Infrastructures 8. JMC Projects Ltd 9. Jains Irrigation Systems Tender Document from ZAWA has been received and reviewed on March 15, 2019. Final tender document incorporating suggested changes received from Zanzibar Water Authority has been reviwed and advised for publishing amonght the pre-qualified companied. Final Tender document has been published by ZAWA on April 03, 2019. Bid opening was extended to May 29, 2019 from May 15, 2019. Bid evaluation report has been received from ZAWA and the same has been reviewed by Exim Bank. Formal letter communicating the comments on the bid evaluation report and requesting ZAWA to review the technical evaluation criteria used for selection of EPC contractors under Lot I, II and III for the captioned LOC was sent on October 09, 2019. ZAWA vide letter No. ZAWA/RIWS/CSS/EXIM/2016/2017/7 dated October 28, 2019 was received in response to our letter no. GOILOC-254/19/1677 dated October 09, 2019 stated that it cannot accept any form of deviations in the bidding process. In the interim Exim Bank received mail from from High Commissioner, Indian Mission, Tanzania, on October 30, 2019 recommending to accept the local norms adodpted in the bid evaluation and convey go-ahead. In response Exim Bank responded to High Commissioner, Indian Mission, Tanzania, on October 31, 2019 Exim Bank is in the process of communicating to ZAWA for once again reviewing the bid evaluation in the interest of the project. Exim Bank vide letter dated November 08, 2019 again requested ZAWA to review the bid evaluation report. However, ZAWA vide letter dated November 12, 2019 informed that they are not in a position to consider any type of deviations in line with the laws, rules and regulations of Zanzibar Public Procurement and Disposal of Public Assets Authority (ZPPDA). In response, Exim Bank advised ZAWA to submit to the Indian Mission in Dar-es-Salam, complete bidding documents received from all the 6 applicants along with any further clarifications for our review. ZAWA vide its letter dated November 20, 2019 informed that they had submitted the applications with Indian Mission. EXIM Bank has already inspected the original bid documents submitted by ZAWA, pertaining to the US $ 92.19 million Line of Credit for rehabilitation and improvement of water supply system in Zanzibar. EXIM Bank has submitted a Report on the Review of the Bid Evaluation Process adopted by ZAWA for selection of EPC Contractor for this water supply project in Zanzibar to MEA, GOI for its review. A mail was received from MEA, DPA on December 24, 2019 communicating that it has been conveyed to our mission in Tanzania requesting that recommendation of the Exim Bank's report on the above mentioned project may be communicated to Government of Tanzania to take suitable course/correction measure. A mail has also been sent by Exim Bank on December 03, 2019 to ZAWA seeking their response in the matter. Response vide letter no. ZAWA/RIWS/CSS/EXIM/2016/2017/2018, dated January 09, 2020 was received from ZAWA seeking Exim Bank’s no objection to proceed with conclusion and recommendation No.3 of “direct opening of the financial bids and award of contract to the L1 bidder” provided in the Bid Evaluation Reported submitted by Exim Bank, which was communicated to ZAWA through the HCI, Tanzania, vide email dated December 24, 2019. Exim Bank vide letter dated January 17, 2020 responded to ZAWA advising to continue with the 2-bid QCBS evaluation process. ZAWA vide letter dated January 27, 2020 confirmed that the comments/observations of Exim Bank made in the Review of Bid Evaluation Report have been agreed to and accepted by ZAWA/Relevant Tanzanian Authorities and they propose to open financial bids proceed with opening of financial bids to award the contract on the basis of the composite score (i.e. continue with the 2-bid QCBS evaluation process). Exim Bank vide mail dated January 28, 2020 advised ZAWA to forward to Exim Bank combined technical and financial evaluation report and draft contract agreement for our review before signing of the contract agreements. We are yet to receive combined technical and financial evaluation report and draft contract agreement from ZAWA.
384 | 143 | 1 | GOILOC-255(P-1) | GOILOC-255 | SUPPLY, INSTALLATION, TESTING AND COMMISSIONING OF PLANT, MACHINERY AND EQUIPMENT | PQ process completed - Contract awarded |  | G-255 | Kenya | 29.95 | Supply, Installation, Testing and Commissioning of Plant Machinery & Equipment for RIVATEX | 29.05 | SPPLY | 2016-09-01 | 2016-10-21 | 2017-04-18 | 2017-07-28 | 2017-07-31 | Pre-Qualified cos. List Lakshmi Machine Works Ltd. Contract Award: Lakshmi Machine Works Ltd.
385 | 144 | 1 | GOILOC-256(P-1) | GOILOC-256
386 | 145 | 1 | GOILOC-257(P-1) | GOILOC-257 | construction of intake structure, screening tank, sedimentation tank, filtration tank, reservoir, laying pipelines (both supply and pumping mains) | PQ process completed - Contract awarded |  | G-257 | Malawi | 23.5 | Construction of a New Water Supply System from Likhubula River in Mulanje to Blantyre | 23.5 | EPC | 2016-12-15 | 2017-01-25 | 2017-09-19 | 2017-09-26 | 2017-10-18 | Pre-Qualified Cos. List: i) Megha Engineering and Infrastructure Ltd. ii) SMC Infrastructure Pvt. Ltd. iii) Technofab Engineering Ltd. iv) JV of WPIL Ltd. and SMS Paryavaran Ltd. Contract award: SMC Infrastructure Pvt. Ltd.
387 | 146 | 1 | GOILOC-258(P-1) | GOILOC-258 | Crude oil Refinery project | PQ process completed - Contract awarded |  | G-258 | Mongolia | 1000 | Oil Refinery project | 72.99 | PMC | 2018-10-26 | 2018-11-26 | 2019-05-13 | 2019-11-19 | 2019-11-29 | Prequalified company: Engineers India Limited [EIL] Contract signed on May 13, 2019
388 | 147 | 1 | GOILOC-259(P-1) | GOILOC-259
389 | 148 | 1 | GOILOC-261(P-1) | GOILOC-261 | Procurement of Passenger-Cargo Ferry Vessel | PQ process completed - Contract yet to be awarded |  | G-261 | Guyana | 10 | Procurement of Passenger-Cargo Ferry Vessel | 18 | SPPLY | 2017-07-05 | 2017-08-04 |  | NA | NA | Project Cost - USD 18 million, out of which USD 8 million will be funded through grant from MEA-LAC division. Pre-Qualified Companies List: i) M/s Shoft Shipyard ii) Garden Reach Ship Builders & Engg Contract Award: Contract is yet to be awarded. Queries were raised by Garden Reach Ship Builders & Engg on the Bid Evaluation Report submitted on 19.09.18 by the GOG. MEA-DPA's advice sought on further course of action. MEA-DPA advised Exim Bank to not enter into any discussions with Govt. of Guyana without its prior approval. Award of Contract is under Dispute.
390 | 149 | 1 | GOILOC-262(P-1) | GOILOC-262 | Housing Project | PQ process completed - Contract yet to be awarded |  | G-262 | Nepal | 750 | Harihar Bhawan, Balmik Campus Project | 22.08 | CC | 2019-07-15 | 2019-08-16 |  | NA | NA | Opened on 30/08/2019. List sent to Government of Nepal on 04.10.2019. List of pre-qualified companies: (a) KEC International, (b) NBCC Limited and (c) Shapoorji and Pallonji Co Pvt Ltd.
391 | 150 | 1 | GOILOC-262(P-2) | GOILOC-262 | Construction
392 | 151 | 1 | GOILOC-263(P-1) | GOILOC-263 | Supply of 9 fixed and 3 mobile High capacity drainage Pumps and ssociated Structures/ Equipments
393 | 152 | 1 | GOILOC-264(P-1) | GOILOC-264 | Setting up a 51MW wind energy farm in Cuba
394 | 153 | 1 | GOILOC-265(P-1) | GOILOC-265 | Setting up of a 50 MW Co-generation power plant in Cuba | PQ process completed - Contract yet to be awarded |  | G-265 | Cuba | 90.3 | Co-generation Power Plant of 50 MW capacity | 90.3 | PMC | 2019-05-14 | 2019-06-28 |  | NA | NA | List of prequalified companies forwarded to BEC, Cuba on 26.08.2019 for undertaking the tendering process are as under:- i. M. N. Dastur & Company Pvt Ltd . ii. MITCON Consultancy and Services Ltd . iii. J.P. Mukherji & Associates Pvt. Ltd The last date for submission of bids was November 28, 2019 under the tenderng process undertaken by Government of Cuba.Bid evaluation report is awaited.
395 | 154 | 1 | GOILOC-266(P-1) | GOILOC-266 | Construction of water supply schemes in 25 towns of Tanzania and water supply project in Zanzibar Urban | PQ process completed - Contract awarded |  | G-266 | Tanzania | 500 | Prequalification of Consultant for I) Preparation of Detailed Project Report (DPR) and II) Project Management Consultant (PMC) for construction of water supply schemes in 25 towns of Tanzania | 7.69 | DPR+PMC | 2018-08-17 | 2018-09-28 | 2019-05-14 | 2019-06-25 | 2019-07-30 | Pre-qualified Companies List: 1) Feedback Infra Pvt. Ltd (Package 1) 2) Tata Consulting Engineers (Package 1 and 2) 3) Venkateshwara Enterprises (Package 1) 4) Wapcos Ltd. (Package 1 and 2) Contract Award: Contract for DPR and PMC has been awarded to WAPCOS Ltd. for the DPR and PMC for Tanzania Mainland. DPR has been forwarded to MEA-DPA for water supply schemes in Tanzania mainland. Contract for WAPCOS Ltd. for DPR has been included under the LOC on July 30, 2019. A letter has been sent to MoW, GO-TZA on August 23, 2019 for amending the contract of WAPCOS Ltd as PMC for modifying the effective date of the contract and defining payment terms. The contract of WAPCOS Ltd as PMC shall be included upon receipt of amendatory contract and revised contract approval form. DPR for the water supply schemes in various towns in Tanzania has been sent to MEA on September 04, 2019 by Government of Tanzania. The PMC has submitted revised detailed project reports reducing the number of towns with a revised estimated cost of USD 460 mn to the Indian Mission on November 04, 2019. The approval of the revised DPR has been received from GOI on January 22, 2020. The DPR approval has been conveyed to Ministry of Water (MoWI), GO-TZA and infor ation has been sought for preparation of the PQ document aswell as conformation on exemption of Taxes..
396 | 155 | 1 | GOILOC-267(P-1) | GOILOC-267 | for rehabilitation of Kankesanthurai Harbour | PQ process completed - Contract yet to be awarded |  | G-267 | Sri Lanka | 45.27 | Rehabilitation of Kankensanthurai Harbour in Sri Lanka | 3 | PMC | 2018-09-24 | 2018-11-02 |  | NA | NA | 1. Pre-Qualified Companies List: Haskoning DHV Consulting Pvt. Ltd. 2. Tender Docmument final clearance given on 06-05-2019 to initiate bidding process. The last date for submission of the bid document was July 8, 2019. Exim Bank on July 10, 2019 has requested GOSL to share the bid evaluation report. Reminder sent on 12.09.2019, 24.10.2019 and 02.12.2019. 3. Bid evaluation report and Draft Contract Agreement has been received from GOSL. Exim Bank on 27.02.2020 has shared it comments on the Draft Contract Agreement.
397 | 156 | 1 | GOILOC-269(P-1) | GOILOC-269 | i) Upgradation and renovating four existing Agriculture Colleges in Lao PDR (including the College in Champasak) and equipping these colleges with updated equipment, curricula, training material and software similar to those being utilized in such institutions in India; ii) Improving extension and training activities, and Research and Development; iii) Establishing pilot projects with irrigation and other associated facilities for inter-alia the cultivation of alternative crops including cash crops in the Borrower’s country.
398 | 157 | 1 | GOILOC-270(P-1) | GOILOC-270 | Preparation of the DPR for upgradation of Military hospitals in Abidjan and construction of Military Hospitals in Bouake, Daloa and Korhogo in Cote d’ Ivoire.
399 | 158 | 1 | GOILOC-271(P-1) | GOILOC-271 | Capitalization of Interest under operative LOCs for change in terms of the existing LOCs
400 | 159 | 1 | GOILOC-273(P-1) | GOILOC-273 | Establishment of 10 Vocational Training Centres and 4 business incubation centres | PQ process completed - Contract awarded |  | G-273 | Rwanda | 81 | Establishment of 10 Vocational Training Centres and 4 business incubation centres in Rwanda | 0.81 | DPR+PMC | 2017-12-28 | 2018-02-09 | 2018-11-01 | 2018-12-19 | 2019-01-18 | Pre-Qualified Companies 1) Crux Consultants Pvt. Ltd. 2) Engineers India Ltd. 3) Mahindra Consulting Engineers Ltd. 4) Octavo Solutions Pvt. Ltd. 5) Rudrabishek Enterprises Pvt. Ltd. 6) STUP Consultants Pvt. Ltd. 7) The National Small Industries Corporation Ltd. 8) Voyants Solutions Pvt. Ltd. 9) WAPCOS Ltd. 10) Shashi Prabhu & Associates and Nitcon Ltd. JV Contract Award: JV of NITCON Ltd. and Shashi Prabhu and Associates.
401 | 160 | 1 | GOILOC-274(P-1) | GOILOC-274 | Infrastructure Development for Power Evacuation Facilities of Rooppur Nuclear Power Plant | PQ process completed - Contract yet to be awarded |  | G-274 | Bangladesh | 4500 | Rooppur–Baghabari 230 KV double circuit 60 Km transmission line | 30.41 | EPC | 2019-06-28 | 2019-07-29 |  | NA | NA | Ten applications received for which evaluation is completed. Prequalified companies are: i. Associated Power Structures Pvt. Ltd. ii. Bajaj Electricals Ltd. iii. Kalpataru Power Transmission Ltd. iv. KEC International Ltd. v. Larsen & Toubro Ltd. vi. Mohan Energy Corporation Ltd. – Unitech Power Transmission Ltd. JV vii. R.S. Infraprojects Pvt. Ltd. viii. Tata Projects Ltd. ix. Transrail Lighting Ltd. Bidding document has been issued to the prequalifeied companies. Four companies namely KEC International Ltd., Kalpataru Power Transmission Ltd. , Transrail Lighting Ltd and Larsen & Toubro Ltd. have submitted the bids. Bid evaluation by PGCB is underway.
402 | 161 | 1 | GOILOC-274(P-2) | GOILOC-274 | Construction of New Dual Gauge Rail Line from Bogra to Shaheed M Mansur Ali Station | PQ process completed - Contract yet to be awarded |  | G-274 | Bangladesh | 4500 | Construction of Dual Gauge Railway Line from Bogra to Shahid M. Mansur Ali Station of Bangladesh Railway [79.30 km Dual Gauge main and 11.35 km Dual gauge loop line] in Bangladesh. | 672.58 | PMC | 2019-02-14 | 2019-04-15 |  | NA | NA | Pre-Qualified Companies : i) Voyants Solutions Pvt Ltd. ii) JV of Rites and Arvee Associates . The details have been shared with the Govt. of Bangladesh for further process of tendering. RFP document has been issued to the bidders . The last date for Bid submision is March 25,2020.
403 | 162 | 1 | GOILOC-274(P-3) | GOILOC-274 | Widening of Ramgarh to Baruerhat Road (38 Km)
404 | 163 | 1 | GOILOC-274(P-4) | GOILOC-274 | Establishment of Solar base Stations in Hard-to-reach areas for strengthening Tele-talk Network Coverage in Bangladesh | PQ process completed - Contract yet to be awarded |  | G-274 | Bangladesh | 4500 | Establishment of Solar base Stations in Hard-to-reach areas for strengthening Tele-talk Network Coverage in Bangladesh | 30 | EPC | 2019-09-24 | 2019-11-08 |  | NA | NA | Opened on November 08, 2019. Five Applications received - (i) Telecommunication Consultants India Ltd (ii) Vihaan Networks Limited (iii) ITI LImited (iv) BEL (v) HFCL. Evaluation underway. Following three companies have qualified: (i) Telecommunication Consultants India Ltd (ii) Vihaan Networks Limited (iii) HFCL Exim Bank has forwarded the shortlist to GOB.GOB to now forward the draft bidding document to Exim Bank.
405 | 164 | 1 | GOILOC-276(P-1) | GOILOC-276 | Upgradation of Regional Hospitals | PQ opened and under evaluation |  | G-276 | Guyana | 17.5 | Upgradation of three regional hospitals in the Co-operative Republic of Guyana | 17.5 | DPR+PMC | 2019-12-10 | 2020-01-10 |  | NA | NA | Four Applications were received and upon evaluation, none of the applicants was found eligible for prequalification in June'2019. PQ is being re-invited with relaxed PQ criteria subject to Govt. of Guyana's confirmation. Govt. of Guyana's final advice on relaxed critieria obtained on December 10, 2019. Exim Bank uploaded the revised PQ document on its website on December 10, 2019. Last date for submission of applications is January 10, 2020. Four Applications have been received and are under evaluation.
406 | 165 | 1 | GOILOC-278(P-1) | GOILOC-278 | Construction and upgradation of Base-Butaro-Kidaho Road Project | PQ process completed - Contract yet to be awarded |  | G-278 | Rwanda | 66.6 | Construction and upgradation of Base-Butaro-Kidaho Road Project | 73.8 | EPC | 2019-10-25 | 2019-12-05 |  | NA | NA | Opened on 05/12/2019. List sent to Government of Rwanda on 23.12.2019. List of pre-qualified companies: i) Afcons Infrastructure Ltd., ii) JMC Projects (India) ltd., iii) Ashoka Buildcon Ltd., iv) Ircon International Ltd. The tender has been published by Government of Rwanda on February 6, 2020 and the last date of submission of the bids is March 10, 2020.
407 | 166 | 1 | GOILOC-279(P-1) | GOILOC-279 |  | PQ opened and under evaluation |  | G-279 | Senegal | 24.5 | Upgradation and Rehabilitation of Health Care Systems in Senegal | 24.5 | DPR+PMC | 2019-11-03 | 2019-12-16 |  | NA | NA | 1. DPR was received from Govt. of Senegal on June 25, 2019. 2. After seeking clarifications, draft PQ document was shared with Govt. of Senegal on October 03, 2019. 3. Exim Bank uploaded the PQ document on 01/11/2019 persuant to receiving confirmation from Govt. of Senegal. 4. The last date for submission of applications was extended to December 16, 2019. 5. Three applications have been received and are under evaluation.
408 | 167 | 1 | GOILOC-280(P-1) | GOILOC-280 | Up-gradation of Transmission Network Infrastructure & Power Generation | PQ process completed - Contract yet to be awarded |  | G-280 | Suriname | 27.5 | Upgradation of Transmission Network Infrastructure in Suriname | 1.375 | PMC | 2018-11-26 | 2018-12-28 |  | NA | NA | Prequalified Companies List: i) WAPCOS ltd. ii) IRCON International Ltd. Tender documents issued on May 23,2019 to the Pre-qualified companies. The last date for bid submission is August 02,2019 WAPCOS Ltd. has been selected as L1.Govt of Suriname to forward the sijgned contract to Exim Bank for inclusion under the LOC
409 | 168 | 1 | GOILOC-281(P-1) | GOILOC-281 | Contract 1 - construction of prefabricated structures, supply and installation of essential equipment for the establishment of 208 health posts in the Central, Copperbelt and Eastern provinces of Zambia and associated external works, valued at USD 2,072,254.85 Contract 2 - for completion of 201 Pre-Fabricated Health Posts in North Western, Northern, Muchinga and Luapala Provinces in Zambia (erstwhile contract of Angelique International Ltd.), signed between the Ministry of Health, Govt. of Zambia and Jaguar Overseas Ltd., valued at USD 15,250,824/- [eligible value of contract under the LOC is USD 12,814,680.00]
410 | 169 | 1 | GOILOC-282(P-1) | GOILOC-282 | Construction of 1600 Borewells with Handpumps and 8 Small Water Systems in Mozambique | PQ process completed - Contract yet to be awarded |  | G-282 | Mozambique | 38 | Construction of 1600 Borewells with Handpumps and 8 Small Water Systems in Mozambique | 38 | PMC | 2019-08-01 | 2019-09-02 |  | NA | NA | 1) PMC PQ uploaded on Exim Bank's website on August 01, 2019. 2) Last date of submission of application was September 02, 2019. 3) Two applications were received from WAPCOS Ltd. and Shah Technical Consultants Ltd. Evaluation was completed on September 30, 2019. The result along with the draft RFP document forwarded to GOM on September 30, 2019. National Directorate of Water Supply and Sanitation [project Authority] vide communication dated November 26, 2019, forwarded the draft RFP document with completed sections on scope, employer’s requirements, evaluation criteria etc. for vetting by Exim Bank. The vetted document was forwarded to GO-MOZ on November 28, 2019 for dissemination to prequalified consultants. Clean copy of RFP was send to Mission of mozambique in India and invitation letters were issued to the bidders on 09.01.2020. Last date for submission of RFP is Feb 28, 2020.
411 | 170 | 1 | GOILOC-283(P-1) | GOILOC-283 | Servicing and maintainance of 3 Chetak Helicoptors
412 | 171 | 1 | GOILOC-284(P-1) | GOILOC-284 |  | PQ document under preparation |  | G-284 (LOC to EBID) | Cote'd'Ivoire | 500 | Potable water supply project in Gueyo and Abidjan | 38 | EPC |  |  |  | NA | NA | PQ Under Preparation. It will be uploaded post approval of PQ committee
413 | 172 | 1 | GOILOC-285(P-1) | GOILOC-285 | Capitalization of the overdue amounts pertaining to interest, penal interest and commitment fee as on the date of restructuring as well as future interest dues and other dues upto July 31, 2020
414 | 173 | 1 | GOILOC-286(P-1) | GOILOC-286 | Capitalization of the overdue amounts pertaining to interest, penal interest and commitment fee as on the date of restructuring as well as future interest dues and other dues upto July 31, 2020
415 | 174 | 1 | GOILOC-287(P-1) | GOILOC-287 | NA
416 | 175 | 1 | GOILOC-288(P-1) | GOILOC-288 | For purpose of financing procurement of defence items from India.
417 | 176 | 1 | GOILOC-289(P-1) | GOILOC-289 | FITL
418 | 177 | 1 | GOILOC-290(P-1) | GOILOC-290 | Mekele Industrial Park 400 kV Power Transmission Project
419 | 178 | 1 | GOILOC-292(P-1) | GOILOC-292 | NA
420 | 179 | 1 | GOILOC-293(P-1) | GOILOC-293 | LOC to capitalise all the existing overdues and future dues falling under the GOILOCs of USD 28.50 mn & USD 20 mn.
421 | 180 | 1 | GOILOC-294(P-1) | GOILOC-294 | New 230 kV interconnection between Ethiopia and Djibouti, 230 kV Combolcha II – Semera Transmission Line along with associated substations extension at Semera, Nagad and Combolcha II
422 | 181 | 1 | GOILOC-295(P-1) | GOILOC-295 | Development of two SEZs & expansion of the Kigali SEZ
423 | 182 | 1 | GOILOC-296(P-1) | GOILOC-296 | Three Agriculture Irrigation Project
424 | 183 | 1 | GOILOC-297(P-1) | GOILOC-297 | Up-gradation of Deka pumping station and river water intake system in Zimbabwe | PQ process completed - Contract yet to be awarded |  | G-181 G-297 | Zimbabwe | 48.1 | Up-gradation of Deka pumping station and river water intake system in Zimbabwe | 35.53 | EPC | 2019-10-01 | 2019-11-15 |  | NA | NA | 1. As the account of Technofab Engineering Ltd [TEL] has been categorised as NPA by 3 Indian Banks, Zimbabwe Power Corporation[ZPC] has cancelled the contract signed with TEL and requested for undertaking a fresh pre-qualification process for the said project. 2. The PQ document inviting fresh applications has been uploaded on Bank's website on October 1, 2019. The last date for submission of the PQ application was extended till November 15, 2019. Exim Bank has completed evaluation of 6 application received in the PQ process. Exim Bank on January 13, 2020 has forwarded the name of the single company pre-qualified in the evalaution process to GOZ. Name of Pre-qualified Company: Afcons Infrastructure Ltd- Vijeta Projects and Infrastructure Ltd [JV].
425 | 184 | 1 | GOILOC-298(P-1) | GOILOC-298 | Renovation/up-gradation of Bulawayo Thermal Power Plant | PQ process completed - Contract yet to be awarded |  | G-246 G-298 | Zimbabwe | 110 | Renovation/up-gradation of Bulawayo Thermal Power Plant | 87 | EPC | 2019-01-07 | 2019-03-14 |  | NA | NA | Pre-Qualified Companies List: i) Bharat Heavy Electricals Ltd [BHEL]. ii) ISGEC Heavy Engineering Ltd [ISGEC] Contract Award: Yet to be awarded. 1. ZPC has initiated the tendering process on 14.11.2019 and the last date for submission of the tender documents was 11.02.2020. The same has been extended till 11.04.2020.
426 | 185 | 1 | GOILOC-299(P-1) | GOILOC-299 | Construction of Parliament building in Gitega and ministerial Buildings in Burundi | PQ document under preparation |  | G-299 | Burundi | 161.36 | Construction of Parliament building in Gitega and ministerial Buildings in Burundi | 161.36 | DPR+PMC |  |  |  | NA | NA | i) LOC was signed on July 2, 2019, However, the LOC is yet to be effective. Ii) Based on the Techno-Economic Feasibility Report received from GOI, the PQ document for selection of DPR/PMC consultants has been prepared and sent to GO-BDI for their comments on Sept 11, 2019. Response awaited from GO-BDI.
427 | 186 | 1 | GOILOC-300(P-1) | GOILOC-300
428 | 187 | 1 | GOILOC-301(P-1) | GOILOC-301 | Supply of Railway Rolling Stock | PQ process completed - Contract yet to be awarded |  | G-301 | Mozambique | 95 | Procurement of railway rolling stock including locomotives, coaches and wagons in Mozambique | 95 | SPPLY | 2019-08-05 | 2019-09-05 |  | NA | NA | PQ was published on August 05, 2019 and the deadline for submission of Application Document was extended from September 06, 2019 to September 16, 2019. Six applications received from Hindustan Engg. Ltd., Modern Industries Ltd., Titagarh Wagons Ltd., Texmaco Rail & Engineering Ltd., Nipha Exports Ltd. and RITES Ltd. Four applicants were qualified: Hindustan Engg. Ltd., Titagarh Wagons Ltd., Texmaco Rail & Engineering Ltd. and RITES Ltd.Vetted tender document was submitted to the GO-MOZ on 08.11.2019 for publishing. The tender document was then published and last date of submission of bid is 10.01.2020 for all three lots.Tender Evualation is under process.
429 | 188 | 1 | GOILOC-323(P-1) | GOILOC-323 | Improving the quality of power supply in Mozambique (Re-offered)
430 | 189 | 1 | GOILOC302(P-1) | GOILOC-302 | Construction of Housing and othe social infrastructure projects
431 | 190 | 1 | GOILOC-303(P-1) | GOILOC-303 |  | PQ opened and under evaluation |  | G-303 | Cuba | 75 | Installation of 75MWp Photovoltaic Solar Parks in Cuba | 75 | DPR | 2019-12-16 | 2020-01-15 |  | NA | NA | i) Exim Bank on August 26, 2019 sent the draft PQ document to GO-Cuba. ii) GO-Cuba on October 21, 2019 sent the draft PQ documents with inputs iii) Draft PQ document for selection of consultant for DPR preparation sent to GO-Cuba for inputs on 11.11.2019. Inputs on PQ received from CUBA on 2.12.2019. iv) Final PQ Uploaded on the website of Exim Bank on 16.12.2019. v) The last date for submission of applications was January 15, 2020. vi) Three applications have been received and are under evaluation.
432 | 191 | 1 | GOILOC-304(P-1) | GOILOC-304 | Rehabilitation and Up gradation of De Melckcentrale N. V. Milk Processing Plant’ | PQ document under preparation |  | G-304 | Suriname | 11.13 | Prequalification of Indian Entities for Rehabilitation and upgradation of De Melkcentrale N. V. Milk Processing Plant in Suriname including Supply, Installation, Testing & Commissioning | 11.13 | SPPLY |  |  |  | NA | NA | PQ under preaparation . Terms of reference received from GO-SUR. Will be launched within a week.
433 | 192 | 1 | GOILOC-305(P-1) | GOILOC-305
434 | 193 | 1 | GOILOC-306(P-1) | GOILOC-306 |  | PQ document under preparation |  | G-306 | D.R. Congo | 33.29 | Installation of 15 MW solar photovoltaic power project at Karawa, DRC | 33.29 | DPR+PMC |  |  |  | NA | NA | Exim Bank has shared the draft PQ Document with GO-DRC on 31.07.2019. Reminder was sent on 28.08.2019. Based on the request of GO-DRC dated 19.09.2019 for re-signing of the agreements, the word copy of the three agreements which were originally signed on 17.03.2019, were re- sent on 20.09.2019 to GO-DRC. One set of duly signed and stamped agreement is still awaited from GO-DRC for making the LOC effective.
435 | 194 | 1 | GOILOC-307(P-1) | GOILOC-307 |  | PQ document under preparation |  | G-307 | D.R. Congo | 25.27 | Installation of 10 MW solar photovoltaic power project at Lusambo, DRC | 25.27 | DPR+PMC |  |  |  | NA | NA | Exim Bank has shared the draft PQ Document with GO-DRC on 31.07.2019. Reminder was sent on 28.08.2019. Based on the request of GO-DRC dated 19.09.2019 for re-signing of the agreements, the word copy of the three agreements which were originally signed on 17.03.2019, were re- sent on 20.09.2019 to GO-DRC. One set of duly signed and stamped agreement is still awaited from GO-DRC for making the LOC effective.
436 | 195 | 1 | GOILOC-308(P-1) | GOILOC-308 |  | PQ document under preparation |  | G-308 | D.R. Congo | 24.55 | Installation of 10 MW solar photovoltaic power project at Mbandaka, DRC | 24.55 | DPR+PMC |  |  |  | NA | NA | Exim Bank has shared the draft PQ Document with GO-DRC on 31.07.2019. Reminder was sent on 28.08.2019. Based on the request of GO-DRC dated 19.09.2019 for re-signing of the agreements, the word copy of the three agreements which were originally signed on 17.03.2019, were re- sent on 20.09.2019 to GO-DRC. One set of duly signed and stamped agreement is still awaited from GO-DRC for making the LOC effective.
437 | 196 | 1 | GOILOC-309(P-1) | GOILOC-309 |  | PQ process completed - Contract awarded |  | G-309 | Maldives | 800 | Development Project of the ‘Addu’ city in Maldives. | 6.71 | DPR+PMC | 2019-08-01 | 2019-09-02 | 2019-12-12 | 2020-01-10 | NA | Pre- Qualified company is L&T IEL - LASA JV. Contract has been signed on 12.12.19. Contract Inclusion Letter dated December 23, 2019 has been received on January 10, 2020. Clarification from MEA was received on February 20, 2020. Contract Inclusion underway.
438 | 197 | 1 | GOILOC-314(P-1) | GOILOC-314 | Procurement of defence equipment from India
439 | 198 | 1 | GOILOC-322(P-1) | GOILOC-322 | Completion of the construction of Foreign policy Training Institute
440 | 199 | 1 | GOILOC-228(P-1) | GOILOC-228 | Design, Ship building , Supply equipment and materials technical douments and technical support for twelve [12] patrol vessels.
441 | 200 | 1 | GOILOC-79(P-1) | GOILOC-79 | Construction, Supply and Installation of Equipment for the works: Binh Bo drainage pumping station , Phu Ninh district
442 | 201 | 1 | GOILOC-61(P-1) | GOILOC-61 | Supply of electro-mechanical equipment and technical services
443 | 202 | 1 | GOILOC-260(P-1) | GOILOC-260 | Detailed Project Report (DPR) for construction of roads in Papua New Guinea from ‘Kimbe’ to ‘Hoskins’ and from ‘Madang’ to ‘Baiyer’ | PQ process completed - Contract yet to be awarded |  | G-260 | Papua New Guinea | 100 | Construction of roads in Papua New Guinea from ‘Kimbe’ to ‘Hoskins’ and from ‘Madang’ to ‘Baiyer’ | 1 | DPR | 2019-07-05 | 2019-08-19 |  | NA | NA | The list of pre-qualified companies were shared with GO-PNG vide letter of November 6, 2019. Draft tender document yet to be received from GO-PNG. Pre-Qualified Companies List: 1 Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. 2 Aicons Engineering Pvt. Ltd. 3 Consulting Engineering Group Ltd. 4 Fortress Infracon Limited and Spectrum Techno Consultants Pvt. Ltd. JV 5 Intercontinental Consultants and Technocrats Pvt. Ltd. 6 LEA Associates South Asia Pvt. Ltd. 7 L.N. Malviya Infra Projects Private Ltd. & Pioneer Infra Consultants Pvt. Ltd. JV 8 Lion Engineering Consultants in JV with Infinite Civil Solutions Pvt. Ltd. 9 L&T Infrastructure Engineering Ltd. 10 Secon Pvt. Ltd. 11 WAPCOS Ltd.
444 | 203 | 1 | GOILOC-97(P-2) | GOILOC-97 | Project for fertilizer production
445 | 204 | 1 | GOILOC-268(P-1) | GOILOC-268 | Completion of unfinished fertilizer plant project covered under an earlier LOC
446 | 205 | 1 | GOILOC-96(P-1) | GOILOC-96 | Upgradation of Thanbayakan Petrochemical Complex
447 | 206 | 1 | GOILOC-180(P-1) | GOILOC-180 | Procurement of farm machinery and implements
448 | 207 | 1 | GOILOC-180(P-2) | GOILOC-180 | Yenwe and Kunchaung irrigation scheme
449 | 208 | 1 | GOILOC-196(P-1) | GOILOC-196 | Procurement of rolling stock, equipment and up-gradation of three major Railway Workshops by procurement of machinery
450 | 209 | 1 | GOILOC-226(P-1) | GOILOC-226 | Implementation of a Microwave Radio Link on the Rhi-Mindat route in Myanmar
451 | 210 | 1 | GOILOC-60(P-2) | GOILOC-60 | Railway projects
452 | 211 | 1 | GOILOC-85(P-1) | GOILOC-85 | (i) Oakshitpin – Thahtay Chaung – Taungup 230 kV Transmission Line and Substation Project; (ii) Taungup – Maei – Ann – Mann 230 kV Transmission Line and Substation project; and (iii) Maei – Kyaukpyu 230 kV Transmission Line and Substation project
453 | 212 | 1 | GOILOC-28(P-1) | GOILOC-28 | Renovation of Thanlyin Refinery
454 | 213 | 1 | GOILOC-327(P-1) | GOILOC-327
455 | 214 | 1 | GOILOC-137(P-2) | GOILOC-137 | Detail, Design, Engineering and Construction of (9.3 MW Production) Kakobola Hydroelectric Power Project
456 | 215 | 1 | GOILOC-24(P-2) | GOILOC-24 | Supply of Machinery and Equipment, Tech. Assistance for Upgradation of Workshops and Training
457 | 216 | 1 | GOILOC-24(P-3) | GOILOC-24 | Supply of locomotives & diesel multiple units
458 | 217 | 1 | GOILOC-24(P-4) | GOILOC-24 | Supply of materials & equipments for chemical deweeding, supply of cars and inspection of gangcars
459 | 218 | 1 | GOILOC-24(P-5) | GOILOC-24 | Supply of means, material & equipment - Mahindra Balero, 4-wheel pickups, mahindra jeeps, Tata buses
460 | 219 | 1 | GOILOC-31(P-2) | GOILOC-31 | Supply of Agro Processing Machinery by S.R.Sood Associates
461 | 220 | 1 | GOILOC-31(P-3) | GOILOC-31 | Supply of Oil processing Equipments by Tinytech Plants
462 | 221 | 1 | GOILOC-31(P-4) | GOILOC-31 | Supply of Trucks by TPS Infrastructure Ltd.
463 | 222 | 1 | GOILOC-31(P-5) | GOILOC-31 | Supply of Vehicles & spare part by TATA motors
464 | 223 | 1 | GOILOC-31(P-6) | GOILOC-31 | Supply of Irrigation Equipment by Kirloskar Brothers Ltd.
465 | 224 | 1 | GOILOC-31(P-7) | GOILOC-31 | Supply of Irrigation Equipment by Jain Irrigation Systems Ltd
466 | 225 | 1 | GOILOC-31(P-8) | GOILOC-31 | Supply of Agricultural Equipment by VST Tillers Ltd
467 | 226 | 1 | GOILOC-31(P-9) | GOILOC-31 | Supply of Vehicles & spare part by TATA motors
468 | 227 | 1 | GOILOC-31(P-10) | GOILOC-31 | Supply of Assorted Vehicle and spare parts by TATA motors
469 | 228 | 1 | GOILOC-31(P-11) | GOILOC-31 | Supply of Agro Processing Machinery by SR Sood Completd
470 | 229 | 1 | GOILOC-31(P-12) | GOILOC-31 | Supply of 232 Units of 60HP Mahindra Agricultural tractors with matching accessories vy Mahindra & Mahindra Ltd.
471 | 230 | 1 | GOILOC-48(P-4B) | GOILOC-48 | Engineering, Procurement, Design, Manufacturing, Testing, Delivery, Installation, Completion and Commissioning of certain facilities for execution of Rural Electrification Extension Project in Gambia
472 | 231 | 1 | GOILOC-28(P-2) | GOILOC-28 | Renovation of Thanlyin Refinery
473 | 232 | 1 | GOILOC-28(P-3) | GOILOC-28 | Renovation of Thanlyin Refinery
474 | 233 | 1 | GOILOC-28(P-4) | GOILOC-28 | Renovation of Thanlyin Refinery
475 | 234 | 1 | GOILOC-28(P-5) | GOILOC-28 | Renovation of Thanlyin Refinery
476 | 235 | 1 | GOILOC-28(P-6) | GOILOC-28 | Renovation of Thanlyin Refinery
477 | 236 | 1 | GOILOC-28(P-7) | GOILOC-28 | Renovation of Thanlyin Refinery
478 | 237 | 1 | GOILOC-133(P-2) | GOILOC-133 | Funding of interest of GOILOC 133
479 | 238 | 1 | GOILOC-36(P-2) | GOILOC-36 | Rural electrification project by Mohan Export Pvt Ltd.
480 | 239 | 1 | GOILOC-36(P-3) | GOILOC-36 | Supply of Equipment for Rural Electrification Project by Angelique International Ltd.
481 | 240 | 1 | GOILOC-11(P-3) | GOILOC-11 | Funding of interest of GOILOC 11
482 | 241 | 1 | GOILOC-66(P-2) | GOILOC-66 | Funding of interest of GOILOC 66
483 | 242 | 1 | GOILOC-43(P-2) | GOILOC-43 | Setting up a cement plant, acquisition of buses and acquisition of equipment for MIBA
484 | 243 | 1 | GOILOC-43(P-3) | GOILOC-43 | Setting up a cement plant, acquisition of buses and acquisition of equipment for MIBA
485 | 244 | 1 | GOILOC-43(P-4) | GOILOC-43 | Setting up a cement plant, acquisition of buses and acquisition of equipment for MIBA
486 | 245 | 1 | GOILOC-43(P-5) | GOILOC-43 | Setting up a cement plant, acquisition of buses and acquisition of equipment for MIBA
487 | 246 | 1 | GOILOC-201(P-4) | GOILOC-201 | [i] Modern Irrigated Agricultural Project; and [ii] Modern Irrigated Agricultural
488 | 247 | 1 | GOILOC-145(P-2) | GOILOC-145 | Supply of pea dehusking and splitting line, electric motors required for the pea dehusking and splitting line, electric hardware, switch gears, power cables, cable trays, etc. and spare parts. The scope of the work also comprised supervision of erection, commissioning of equipment including training
489 | 248 | 1 | GPFTF-41.9(P-1) | GPFTF-41.9 | SINGA-GEDARIF transmission and Sub-Station Project
490 | 249 | 1 | GOILOC-249(P-15) | GOILOC-249 | Establishment of IT/Hi-Tech Park at District Level (Twelve Districts) project
491 | 250 | 1 | GOILOC-34(P-2) | GOILOC-34 | Agricultural projects including acquisition of tractors, harvesters, agricultural processing equipment
492 | 251 | 1 | GOILOC-57(P-2) | GOILOC-57 | Multifunctional platforms, roller flour mill cereal processing units & bakery plant
493 | 252 | 1 | GOILOC-16(P-2) | GOILOC-16 | Railway rehabilitation
494 | 253 | 1 | GOILOC-16(P-4) | GOILOC-16 | Railway rehabilitation
495 | 254 | 1 | GOILOC-16(P-5) | GOILOC-16 | Railway rehabilitation
496 | 255 | 1 | GOILOC-16(P-6) | GOILOC-16 | Railway rehabilitation
497 | 256 | 1 | GOILOC-16(P-7) | GOILOC-16 | Railway rehabilitation
498 | 257 | 1 | GOILOC-16(P-8) | GOILOC-16 | Railway rehabilitation
499 | 258 | 1 | GOILOC-16(P-9) | GOILOC-16 | Railway rehabilitation
500 | 259 | 1 | GOILOC-16(P-10) | GOILOC-16 | Railway rehabilitation
501 | 260 | 1 | GOILOC-16(P-11) | GOILOC-16 | Railway rehabilitation
502 | 261 | 1 | GOILOC-16(P-12) | GOILOC-16 | Railway rehabilitation
503 | 262 | 1 | GOILOC-16(P-13) | GOILOC-16 | Railway rehabilitation
504 | 263 | 1 | GOILOC-16(P-14) | GOILOC-16 | Railway rehabilitation
505 | 264 | 1 | GOILOC-16(P-15) | GOILOC-16 | Railway rehabilitation
506 | 265 | 1 | GOILOC-16(P-16) | GOILOC-16 | Railway rehabilitation
507 | 266 | 1 | GOILOC-16(P-17) | GOILOC-16 | Railway rehabilitation
508 | 267 | 1 | GOILOC-16(P-18) | GOILOC-16 | Railway rehabilitation
509 | 268 | 1 | GOILOC-16(P-19) | GOILOC-16 | Railway rehabilitation
510 | 269 | 1 | GOILOC-16(P-20) | GOILOC-16 | Railway rehabilitation
511 | 270 | 1 | GOILOC-16(P-21) | GOILOC-16 | Railway rehabilitation
512 | 271 | 1 | GOILOC-16(P-22) | GOILOC-16 | Railway rehabilitation
513 | 272 | 1 | GOILOC-16(P-23) | GOILOC-16 | Railway rehabilitation
514 | 273 | 1 | GOILOC-16(P-24) | GOILOC-16 | Railway rehabilitation
515 | 274 | 1 | GOILOC-40(P-2) | GOILOC-40 | Rural electrification and setting up of agro machinery and tractor assembly plant
516 | 275 | 1 | GOILOC-40(P-3) | GOILOC-40 | Rural electrification and setting up of agro machinery and tractor assembly plant
517 | 276 | 1 | GOILOC-53(P-2) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
518 | 277 | 1 | GOILOC-53(P-3) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
519 | 278 | 1 | GOILOC-53(P-4) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
520 | 279 | 1 | GOILOC-53(P-5) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
521 | 280 | 1 | GOILOC-53(P-6) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
522 | 281 | 1 | GOILOC-53(P-7) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
523 | 282 | 1 | GOILOC-53(P-8) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
524 | 283 | 1 | GOILOC-53(P-9) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
525 | 284 | 1 | GOILOC-53(P-10) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
526 | 285 | 1 | GOILOC-53(P-11) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
527 | 286 | 1 | GOILOC-53(P-12) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
528 | 287 | 1 | GOILOC-53(P-13) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
529 | 288 | 1 | GOILOC-53(P-15) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
530 | 289 | 1 | GOILOC-53(P-16) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
531 | 290 | 1 | GOILOC-53(P-17) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
532 | 291 | 1 | GOILOC-53(P-18) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
533 | 292 | 1 | GOILOC-53(P-19) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
534 | 293 | 1 | GOILOC-53(P-20) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
535 | 294 | 1 | GOILOC-53(P-21) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
536 | 295 | 1 | GOILOC-53(P-22) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
537 | 296 | 1 | GOILOC-31(P-13) | GOILOC-31 | 232 Units of 60HP Mahindra Agricultural tractors with matching accessories
538 | 297 | 1 | GOILOC-240(P-1) | GOILOC-240 | Construction of social housing | PQ process completed - Contract yet to be awarded |  | G-240 | Mauritius | 500 | E-Health Project | 16 | SPPLY | 2019-03-15 | 2019-05-31 |  | NA | NA | Seven applications were received for which evaluation is completed. Prequalified companies are: TCIL-SRIT JV and EIT Services. Vetted tender document was forwarded to HSCC/MOHQL on 04.09.2019. The tender was diseminated by HSCC on 25.10.2019 and last date for submission of bid was 24.01.2020. The Bids are now evaluated by HSCC and MOH. Awaiting techninical bid evaluation report for vetting purpose.
539 | 298 | 1 | GOILOC-240(P-2) | GOILOC-240 | Metro Express Ltd
540 | 299 | 1 | GOILOC-240(P-3) | GOILOC-240 | Acquisition of 16 incinerators
541 | 300 | 1 | GOILOC-240(P-4) | GOILOC-240 | Mauritius Police Academy
542 | 301 | 1 | GOILOC-240(P-5) | GOILOC-240 | Forensic Science Laboratory
543 | 302 | 1 | GOILOC-240(P-6) | GOILOC-240 | National Archives & Library
544 | 303 | 1 | GOILOC-201(P-1) | GOILOC-201 | Project Management Consultancy for Export Targeting Modern Irrigated Agricliuture Project in Rwanda
545 | 304 | 1 | GOILOC-201(P-2) | GOILOC-201 | Capacity Building and Training under the Export Targeted Modern Irrigation Project in Rwanda
1 | 305 | 1 | GOILOC-1(P-1) | GOILOC-1 | General purpose: Contracts approved include export of electrification equipment, photovoltaic cells, diesel coaches, rehabilitation of locomotives, textile machinery, copper rods etc.
2 | 306 | 1 | GOILOC-3(P-1) | GOILOC-3 | General purpose - Contracts approved include supply of water drilling machinery, equipments, accessories, components and spares, support vehicles, water and fuel tankers and electrical equipments
3 | 307 | 1 | GOILOC-4(P-1) | GOILOC-4 | Electrification of Gaza province
4 | 308 | 1 | GOILOC-5(P-1) | GOILOC-5 | Transfer of water drilling technology and equipments
5 | 309 | 1 | GOILOC-7(P-1) | GOILOC-7 | Supply of Four wheel tractors
6 | 310 | 1 | GOILOC-7(P-2) | GOILOC-7 | Supply of Portable Diesel Engine
7 | 311 | 1 | GOILOC-7(P-3) | GOILOC-7 | Consultancy services (Irrigation development feasibility study)
8 | 312 | 1 | GOILOC-7(P-4) | GOILOC-7 | Supply of Irrigation Equipment
9 | 313 | 1 | GOILOC-7(P-5) | GOILOC-7 | Supply of Pump sets and spare parts and generating sets
10 | 314 | 1 | GOILOC-7(P-6) | GOILOC-7 | Supply of Equipment for sprinkler and drip irrigation
11 | 315 | 1 | GOILOC-9(P-1) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
12 | 316 | 1 | GOILOC-9(P-2) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
13 | 317 | 1 | GOILOC-9(P-3) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
14 | 318 | 1 | GOILOC-9(P-4) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
15 | 319 | 1 | GOILOC-9(P-5) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
16 | 320 | 1 | GOILOC-9(P-6) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
17 | 321 | 1 | GOILOC-9(P-7) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
18 | 322 | 1 | GOILOC-9(P-8) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
19 | 323 | 1 | GOILOC-9(P-9) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
20 | 324 | 1 | GOILOC-9(P-10) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
21 | 325 | 1 | GOILOC-9(P-11) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
22 | 326 | 1 | GOILOC-9(P-12) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
23 | 327 | 1 | GOILOC-9(P-13) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
24 | 328 | 1 | GOILOC-9(P-14) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
25 | 329 | 1 | GOILOC-9(P-15) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
26 | 330 | 1 | GOILOC-9(P-16) | GOILOC-9 | Enhancing productivity of rice, wheat, maize cultivation
27 | 331 | 1 | GOILOC-10(P-1) | GOILOC-10 | Solar Photo Voltaic Module Manufacturing Plant
28 | 332 | 1 | GOILOC-11(P-1) | GOILOC-11 | General Purpose. Three contracts – one for supply of diesel generating sets and pumps, second for setting up a mini cement plant and a third contract for civil works
29 | 333 | 1 | GOILOC-11(P-2) | GOILOC-11 | General Purpose. Three contracts – one for supply of diesel generating sets and pumps, second for setting up a mini cement plant and a third contract for civil works
30 | 334 | 1 | GOILOC-12(P-1) | GOILOC-12 | General Purpose - Contracts approved include export of TATA buses, motor vehicles, motor cycles and supply of vocational tool kits
31 | 335 | 1 | GOILOC-12(P-2) | GOILOC-12 | General Purpose - Contracts approved include export of TATA buses, motor vehicles, motor cycles and supply of vocational tool kits
32 | 336 | 1 | GOILOC-12(P-3) | GOILOC-12 | General Purpose - Contracts approved include export of TATA buses, motor vehicles, motor cycles and supply of vocational tool kits
33 | 337 | 1 | GOILOC-12(P-4) | GOILOC-12 | General Purpose - Contracts approved include export of TATA buses, motor vehicles, motor cycles and supply of vocational tool kits
34 | 338 | 1 | GOILOC-13(P-1) | GOILOC-13 | Establishment of an OFC link between Moreh and Mandalay, an ADSL high-speed data link in Yangon area and a reduced number of COR-DECT lines
35 | 339 | 1 | GOILOC-15(P-1) | GOILOC-15 | Rural electrification
36 | 340 | 1 | GOILOC-16(P-1) | GOILOC-16 | Railway rehabilitation
37 | 341 | 1 | GOILOC-20(P-1) | GOILOC-20
38 | 342 | 1 | GOILOC-24(P-1) | GOILOC-24 | Supply of Machinery and Equipment, Tech. Assistance for Upgradation of Workshops and Training
39 | 343 | 1 | GOILOC-25(P-1) | GOILOC-25 | supply of coaches & other equipment
40 | 344 | 1 | GOILOC-27(P-1) | GOILOC-27 | Supply of materials & equipments for chemical deweeding, supply of cars and inspection of gangcars
41 | 345 | 1 | GOILOC-29(P-1) | GOILOC-29 | Supply of means, material & equipment - Mahindra Balero, 4-wheel pickups, mahindra jeeps, Tata buses | PQ process completed - Contract yet to be awarded |  | G-29 | Sri Lanka | 100 | Procurement of 750 [4 wheel Vehicle SUV/MUV] in Sri Lanka | 20 | SPPLY | 2019-09-16 | 2019-10-16 |  | NA | NA | 1. Based on the project details and specifications of the Vehicle received from GOSL , Exim Bank has prepared PQ document. 2.The PQ document was uploaded on the Bank's website on September 16, 2019 and the last date for submission of the PQ application was October 16, 2019. 2 applications have been received and both have qualified . Exim Bank on 19.11.2019 has shared the names of both the pre-qualified companies with GOSL and requested for sharing of the Draft Tender document for review. Reminder sent to GOSL on January 29, 2020. Response from GOSL is awaited.
42 | 346 | 1 | GOILOC-30(P-1) | GOILOC-30 | Supply of water pumps to National Water Commission
43 | 347 | 1 | GOILOC-31(P-1) | GOILOC-31 | Supply of Vehicles & spare part by TATA motors
44 | 348 | 1 | GOILOC-32(P-1) | GOILOC-32 | Acquisition of railway coaches and locomotives from India
45 | 349 | 1 | GOILOC-33(P-1) | GOILOC-33 | Restructuring the sugar industry in Fiji Islands
46 | 350 | 1 | GOILOC-34(P-1) | GOILOC-34 | Agricultural projects including acquisition of tractors, harvesters, agricultural processing equipment
47 | 351 | 1 | GOILOC-35(P-1) | GOILOC-35 | Supply of machinery and equipment, spares and services for cotton yarn plant
48 | 352 | 1 | GOILOC-35(P-2) | GOILOC-35 | supply of Additional equipment for plant for assembly of agriculture equipment
49 | 353 | 1 | GOILOC-35(P-3) | GOILOC-35 | machinery and equipment, spares and services for plant for assembly of agricultural equipment
50 | 354 | 1 | GOILOC-35(P-4) | GOILOC-35 | machinery and equipment, spares and services for bicycle plant
51 | 355 | 1 | GOILOC-35(P-5) | GOILOC-35 | machinery and equipment, spares and services for steel billet plant and rolling plant mill
52 | 356 | 1 | GOILOC-36(P-1) | GOILOC-36 | Construction of Presidential Office by Shapoorji Pallonji & Co. Ltd.
53 | 357 | 1 | GOILOC-37(P-1) | GOILOC-37
54 | 358 | 1 | GOILOC-38(P-1) | GOILOC-38 | Supply of Buses and Spare Parts,
55 | 359 | 1 | GOILOC-38(P-2) | GOILOC-38 | construction of vegetable oil processing plant
56 | 360 | 1 | GOILOC-38(P-3) | GOILOC-38 | construction of cashew nut processing plant
57 | 361 | 1 | GOILOC-38(P-4) | GOILOC-38 | chip-making & packing, liquid sugar, cassava starch making plants
58 | 362 | 1 | GOILOC-40(P-1) | GOILOC-40 | Rural electrification and setting up of agro machinery and tractor assembly plant
59 | 363 | 1 | GOILOC-41(P-1) | GOILOC-41 | Export of communication equipment, medical equipment and transportation equipment
60 | 364 | 1 | GOILOC-43(P-1) | GOILOC-43 | Setting up a cement plant, acquisition of buses and acquisition of equipment for MIBA
61 | 365 | 1 | GOILOC-44(P-1) | GOILOC-44 | Supply of 500 tractors with spares and assembly
62 | 366 | 1 | GOILOC-45(P-1) | GOILOC-45 | Food processing & agricultural sector
63 | 367 | 1 | GOILOC-45(P-2) | GOILOC-45 | Rural Electrification Project
64 | 368 | 1 | GOILOC-46(P-1) | GOILOC-46 | Buses, automobiles, flour mills and motor pumps.
65 | 369 | 1 | GOILOC-47(P-1) | GOILOC-47 | Electrification of Gaza province
66 | 370 | 1 | GOILOC-48(P-1) | GOILOC-48 | Supply of Buses and Spare Parts
67 | 371 | 1 | GOILOC-48(P-2) | GOILOC-48 | Supply and installation of equipments for health facilities
68 | 372 | 1 | GOILOC-48(P-3) | GOILOC-48 | Supply and execution of rehabilitation and extension of the power distribution network of the town of Labe
69 | 373 | 1 | GOILOC-48(P-4A) | GOILOC-48 | Engineering, Procurement, Design, Manufacturing, Testing, Delivery, Installation, Completion and Commissioning of certain facilities for execution of Rural Electrification Extension Project in Gambia
70 | 374 | 1 | GOILOC-48(P-5) | GOILOC-48 | Supply of Equipment, material and spare parts
71 | 375 | 1 | GOILOC-48(P-6) | GOILOC-48 | Design, Manufacture, Testing, Delivery, Assembly, and Commissioning of the facility related to the project rehabilitation and Extension of the Electrical Energy Distribution Network of Compagnie Energie Electrique Du Togo (CEET)
72 | 376 | 1 | GOILOC-48(P-7) | GOILOC-48 | Supply of 6 borehole workshops and related technical materials
73 | 377 | 1 | GOILOC-48(P-8) | GOILOC-48 | Supply of goods and equipments for electrification of 19 Rural Communities in the administrative Divisions of Alibouri and Borgou in Benin
74 | 378 | 1 | GOILOC-48(P-9) | GOILOC-48 | Supply of Transmission Line Single Circuit 225 KV Interconnection and completion of Substation (Koutiala-Segou) - Mali- Cote divoire
75 | 379 | 1 | GOILOC-48(P-10) | GOILOC-48 | Supply and installation of materials for rolling stock, software, computer material, in respect of the Tomato project.
76 | 380 | 1 | GOILOC-48(P-11) | GOILOC-48 | Modernization and expansion of Sierra Leone National Telecommunications [SIERRATEL]
77 | 381 | 1 | GOILOC-48(P-12) | GOILOC-48 | For supply of 104 fire tenders and accessories to Ghana
78 | 382 | 1 | GOILOC-48(P-13) | GOILOC-48 | Self Help Electrification Project [SHEP-4] in Ghana | PQ process completed - Contract awarded |  | G48[13] (LOC to EBID) | Ghana | 250.00 (Project of USD 14.97 mn) | Self Help Electrification Project [SHEP-4] in the Ashanti and Brong Ahafo Regions in the Republic of Ghana | 0.5 | DPR+PMC | 2017-10-27 | 2017-12-12 | 2018-12-10 | 2019-03-01 | 2019-03-20 | Pre-Qualified Companies List: i) Electrical Research And Development Association ii) Tata Power Delhi Distribution Ltd. iii) Voyants Solutions Pvt. Ltd. iv) WAPCOS Ltd. Contract Award: Contract awarded to WAPCOS included under the LOC on 20.03.2019.
79 | 383 | 1 | GOILOC-49(P-1) | GOILOC-49 | Energy transmission and distribution project
80 | 384 | 1 | GOILOC-50(P-1) | GOILOC-50 | Supply of Agro commidities
81 | 385 | 1 | GOILOC-52(P-1) | GOILOC-52 | Rehabilitation of Devighat Hydro Power Plant
82 | 386 | 1 | GOILOC-52(P-2) | GOILOC-52 | Upgrading of Tulsipur-Salyan Road
83 | 387 | 1 | GOILOC-52(P-3) | GOILOC-52 | Upgrading of Sanfebagar-Mangalsen Road
84 | 388 | 1 | GOILOC-52(P-4) | GOILOC-52 | Upgrading of Chndranigahapur-Gaur Road
85 | 389 | 1 | GOILOC-52(P-5) | GOILOC-52 | Upgrading of Bhaluwang-Pyuthan Road
86 | 390 | 1 | GOILOC-52(P-6) | GOILOC-52 | Upgrading of Chakchake-Liwang Road
87 | 391 | 1 | GOILOC-52(P-7) | GOILOC-52 | Upgrading of Surkhet-Ranimatta-Dailekh Road
88 | 392 | 1 | GOILOC-52(P-8) | GOILOC-52 | Upgrading of Sanfebagar - Martadi Road
89 | 393 | 1 | GOILOC-52(P-9) | GOILOC-52 | Upgrading of Hilepani-Diktel Road
90 | 394 | 1 | GOILOC-52(P-10) | GOILOC-52 | Upgrading of Basantpur-Myanglang Road
91 | 395 | 1 | GOILOC-52(P-11) | GOILOC-52 | Upgrading Ameliya Tulsipur Road
92 | 396 | 1 | GOILOC-52(P-12) | GOILOC-52 | Upgrading of Maldhunga- Beni Road
93 | 397 | 1 | GOILOC-52(P-13) | GOILOC-52 | Upgrading of Rajbiraj-Sakhada, Rajbiraj-Bhardah and Rajbiraj-Rupani Roads
94 | 398 | 1 | GOILOC-52(P-14) | GOILOC-52 | 400 kV D/C Dhalkebar-Bhittamod [Nepal border] section of 400 kV D/C Dhalkebar [Nepal] – Muzaffarpur [India] transmission line
95 | 399 | 1 | GOILOC-52(P-15) | GOILOC-52 | Civil Works and Design, Manufacture, Supply, Erection, Testing and Commissioning of Hydro Mechanical Works for “Rahughat Hydroelectric Project-40 MW”
96 | 400 | 1 | GOILOC-53(P-1) | GOILOC-53 | Supply of agricultural inputs for the Sudanese Agricultural Bank, technical and laboratory equipment to Higher Educational Institutions, scientific equipments for Ministry of Science and Technology, solar electrification & meeting requirements of Sudan Railways
97 | 401 | 1 | GOILOC-54(P-1) | GOILOC-54
98 | 402 | 1 | GOILOC-55(P-1) | GOILOC-55 | Traffic signaling system project
99 | 403 | 1 | GOILOC-56(P-1) | GOILOC-56
100 | 404 | 1 | GOILOC-57(P-1) | GOILOC-57 | 300 Pick up Double cabin TATA telcoline 4x4, 5 TATA Safari DICOR, 50 TATA 207 DI Single cabin
101 | 405 | 1 | GOILOC-58(P-1) | GOILOC-58 | Development of Irrigation schemes in the Champassack Province
102 | 406 | 1 | GOILOC-59(P-1) | GOILOC-59 | Plant for assembly and manufacturing of Tata vehicles
103 | 407 | 1 | GOILOC-60(P-1) | GOILOC-60 | Railway projects
104 | 408 | 1 | GPFTF-350(P-1) | GPFTF-350 | Setting up 4 x 125 MW Kosti Combined Cycle Power Plant in Sudan to be executed by Bharat Heavy Electricals Ltd. (BHEL).
105 | 409 | 1 | GOILOC-65(P-1) | GOILOC-65 | Electricity transmission and distribution project from Cote dIvoire to Mali
106 | 410 | 1 | GOILOC-66(P-1) | GOILOC-66 | 600 TPD Ali Sabieh Cement Plant Project , Phase I
107 | 411 | 1 | GOILOC-67(P-1) | GOILOC-67 | Engineering, Procurement and Construction (EPC) Contract of 28 MW Nyabarongo Hydroelectric Project
108 | 412 | 1 | GOILOC-68(P-1) | GOILOC-68 | Completion of Mali-Ivory Coast Interconnection Link for integrating the national power grids of the two countries.
109 | 413 | 1 | GOILOC-70(P-1) | GOILOC-70 | SINGA-GEDARIF Transmission line extension to Galabat, micro-industrial projects and development of livestock production and services
110 | 414 | 1 | GOILOC-71(P-1) | GOILOC-71
111 | 415 | 1 | GOILOC-73(P-1) | GOILOC-73 | Development of sugar industry
112 | 416 | 1 | GOILOC-74(P-1) | GOILOC-74 | Electricity transmission and distribution project from Cote dIvoire to Mali
113 | 417 | 1 | GOILOC-75(P-1) | GOILOC-75 | Water Supply Project
114 | 418 | 1 | GOILOC-78(P-1) | GOILOC-78
115 | 419 | 1 | GOILOC-78(P-2) | GOILOC-78
116 | 420 | 1 | GOILOC-78(P-3) | GOILOC-78
117 | 421 | 1 | GOILOC-80(P-1) | GOILOC-80 | Foreign Policy Training Institution, railway corridors and agro processing plant
118 | 422 | 1 | GOILOC-81(P-1) | GOILOC-81 | Strengthening the capacity of transmission line project between Kratie and Stung Treng
119 | 423 | 1 | GOILOC-82(P-1) | GOILOC-82 | Mashkour (earlier Elduem) Sugar Project at White Nile State (Ist tranche of US $ 150 mn)
120 | 424 | 1 | GOILOC-83(P-1) | GOILOC-83 | supply of irrigation, storage, tobacco threshing plant and one village- one project
121 | 425 | 1 | GOILOC-84(P-1) | GOILOC-84 | Paksong S/S – Jiangxai 115 KV, double circuit Transmission Line Project , Nam Song 7.5 MW hydropower project and Equipment for Rural electrification Phase 2 Project
122 | 426 | 1 | GOILOC-86(P-1) | GOILOC-86 | Architectural Design and Supervision of Construction of the National Assembly Building in Gambia
123 | 427 | 1 | GOILOC-86(P-2) | GOILOC-86 | Construction of the National Assembly Building in Gambia
124 | 428 | 1 | GOILOC-87(P-1) | GOILOC-87 | Construction of Coconut Fibre Processing Plant
125 | 429 | 1 | GOILOC-87(P-2) | GOILOC-87 | supply of fish & shrimp processing plant, fish feed plant and fish farming equipment on turnkey contract basis
126 | 430 | 1 | GOILOC-87(P-3) | GOILOC-87 | Designing, architectural study, technical study and construction to accommodate the enterprises of The Free Zone of Biotechnology and Information Technology and Communication (ZBTIC)
127 | 431 | 1 | GOILOC-87(P-4) | GOILOC-87 | Supply and installation of equipments
128 | 432 | 1 | GOILOC-88(P-1) | GOILOC-88 | Purchases from BEL, HAL and Ordinance Factory Board
129 | 433 | 1 | GOILOC-89(P-1) | GOILOC-89 | Transfer of water drilling technology and equipments
130 | 434 | 1 | GOILOC-90(P-1) | GOILOC-90 | Supply of tractors, pumps, spare parts, training, assembly operations, after sales service support and assembly line equipments;
131 | 435 | 1 | GOILOC-91(P-1) | GOILOC-91 | Diesel Multiple Units Maintenance Facilities
132 | 436 | 1 | GOILOC-91(P-2) | GOILOC-91 | Supply, installation and commissioning of machinery & plants
133 | 437 | 1 | GOILOC-91(P-3) | GOILOC-91 | HRD Training of 600 Sri Lanka Railways personnel
134 | 438 | 1 | GOILOC-91(P-4) | GOILOC-91 | Supply of 15 diesel multiple units
135 | 439 | 1 | GOILOC-91(P-5) | GOILOC-91 | Supply of capital unit exchange equipment (spare parts) for existing M8 class locomotives
136 | 440 | 1 | GOILOC-91(P-6) | GOILOC-91 | Upgradation of Colombo-Matara Coastal Railway Line
137 | 441 | 1 | GOILOC-92(P-1) | GOILOC-92 | Rural electrification
138 | 442 | 1 | GOILOC-93(P-1) | GOILOC-93
139 | 443 | 1 | GOILOC-93(P-2) | GOILOC-93
140 | 444 | 1 | GOILOC-94(P-1) | GOILOC-94 | (a) Setting up of a Modern dry process cement plant of 400 TPD capacity and (b) Procurement of 100 buses for internal transport
141 | 445 | 1 | GOILOC-95(P-1) | GOILOC-95 | (a) Agricultural Machinery and equipment (b) Construction of 30 Rice Mill Buildings, Rice Stores and Drying Floors
142 | 446 | 1 | GOILOC-97(P-1) | GOILOC-97 | Project for Rice productivity
143 | 447 | 1 | GOILOC-98(P-1) | GOILOC-98 | Development of sugar industry
144 | 448 | 1 | GOILOC-99(P-1) | GOILOC-99 | Supply of Turbines, Generators, Main Inlet Valves, Speed Governors and Excitation System plus Supervision of Erection and Commissioning
145 | 449 | 1 | GOILOC-100(P-1) | GOILOC-100 | (a) Rehabilitation of six-power stations (b) Purchase of three power transformers (c ) Rehabilitation as well as erection of power lines between various places in Niger
146 | 450 | 1 | GOILOC-101(P-1) | GOILOC-101 | To finance IT Park Project which will comprise construction of building and (a) incubator facility, (b) research and learning centre and (c) technology park and administrative facility.
147 | 451 | 1 | GOILOC-102(P-1) | GOILOC-102 | Rural Electrification Project in the provinces of Inhambane, Zambezi and Nampula
148 | 452 | 1 | GOILOC-103(P-1) | GOILOC-103 | Supply of ten crash fire tenders by BEML
149 | 453 | 1 | GOILOC-104(P-1) | GOILOC-104 | Supply of Machinery and Equipment for Maize Farm Plantation Project
150 | 454 | 1 | GOILOC-105(P-1) | GOILOC-105 | Reconstruction of Grodno-II Power Plant (100-130 MW) Project in Belarus
151 | 455 | 1 | GOILOC-106(P-1) | GOILOC-106 | Improved fish harvesting & fish processing project and
152 | 456 | 1 | GOILOC-107(P-1) | GOILOC-107 | Partly finance Tishreen Thermal Power Project (2 x 200 MW) by BHEL
153 | 457 | 1 | GOILOC-108(P-1) | GOILOC-108 | Installation of hand pumps and submersible pumps
154 | 458 | 1 | GOILOC-109(P-1) | GOILOC-109 | Completion of Mali-Ivory Coast Interconnection Link for integrating the national power grids of the two countries.
155 | 459 | 1 | GOILOC-110(P-1) | GOILOC-110 | Rehabilitation of existing water facility
156 | 460 | 1 | GOILOC-111(P-1) | GOILOC-111
157 | 461 | 1 | GOILOC-112(P-1) | GOILOC-112 | Engineering, Procurement and Construction (EPC) Contract of 28 MW Nyabarongo Hydroelectric Project
158 | 462 | 1 | GOILOC-113(P-1) | GOILOC-113 | Multipurpose agricultural projects and educational projects
159 | 463 | 1 | GOILOC-114(P-1) | GOILOC-114 | Acquiring, Installing and Commissioning of Fixed and Mobile Irrigation Pumps in Guyana
160 | 464 | 1 | GOILOC-115(P-1) | GOILOC-115 | (A) Railway equipment (USD 10.25 mn)
161 | 465 | 1 | GOILOC-115(P-2) | GOILOC-115 | (B) agricultural equipment (USD 4.25 mn)
162 | 466 | 1 | GOILOC-115(P-3) | GOILOC-115 | (C) feasibility study for setting up a cyber city (USD 0.50 mn)
163 | 467 | 1 | GOILOC-122(P-1) | GOILOC-122 | Cotton
164 | 468 | 1 | GOILOC-116(P-1) | GOILOC-116 | Industrial Park Project
165 | 469 | 1 | GOILOC-117(P-1) | GOILOC-117
166 | 470 | 1 | GOILOC-118(P-1) | GOILOC-118
167 | 471 | 1 | GOILOC-119(P-1) | GOILOC-119 | Atal Bihari Vajpayee Centre for Excellence in Information Technology and Outsourcing [ABV-CEITCO] Project, consisting of two packages; Package -I for the construction of the Building and related works and Package -II, setting up of IT centre, development of training modules , training etc. | PQ process completed - Contract yet to be awarded |  | G119 | Mongolia | 20 | India Mongolia Joint Information Technology and Outsourcing Centre (IMJIT) Project | 10.16 | EPC | 2019-06-10 | 2019-07-30 |  | NA | NA | Four applications received for which evaluationhas been completed. Prequalified companies are: [i] NBCC [India] Ltd. [ii] KEC International Limited [iii] JV of VASCON-ASHOKA Buildcon Ltd. [iv] P.K.Saxena Contractor Bidding document has been issued to the pre-qualified companies by GOM. Last date of biud submission was Jan31,2020. Only P.K.Saxena Contractor has submitted the bid. GoM has forwarded the Bid Evaluation Report and approved P.K.Saxena contractors under package -I. Exim Bank has advised GOM to undertake necessary steps to finalise the contract and sent the same for inclusion under the LOC.
168 | 472 | 1 | GOILOC-120(P-1) | GOILOC-120 | Vocational training center for empowerment of youth and women
169 | 473 | 1 | GOILOC-121(P-1) | GOILOC-121 | Supply and erection of 225 kv line between Laboa abd Boundiali alongwith extension substation at Laboa
170 | 474 | 1 | GOILOC-121(P-2) | GOILOC-121 | Supply and erection of 225 kv line between Boundiali and Ferkessedougou alongwith extension substation at Ferkessedougou and creation of new substation at Boundiali
171 | 475 | 1 | GOILOC-123(P-1) | GOILOC-123 | Agriculture and food processing projects
172 | 476 | 1 | GOILOC-124(P-1) | GOILOC-124
173 | 477 | 1 | GOILOC-125(P-1) | GOILOC-125 | Financing the purchase of 679 (earlier 723) vehicles
174 | 478 | 1 | GOILOC-126(P-1) | GOILOC-126 | Upgrading of Colombo- Matara Coastal Railway Line
175 | 479 | 1 | GOILOC-126(P-2) | GOILOC-126 | Supply of 5 diesel multiple units
176 | 480 | 1 | GOILOC-126(P-3) | GOILOC-126 | Supply of 3 2300 HP (M8 ‘A’ type) Diesel Electric Locomotives
177 | 481 | 1 | GOILOC-127(P-1) | GOILOC-127 | Purchase of helicopters from HAL
178 | 482 | 1 | GOILOC-128(P-1) | GOILOC-128 | construction of 30 storehouses and offices in prefabricated material to house paddy processing and storage units: Eligible Contract value USD 12,306,282.00 [CFR]
179 | 483 | 1 | GOILOC-128(P-2) | GOILOC-128 | Supply of Rolling Stock: Eligible Contract value USD 3,727,500.00 [CFR] Railways
180 | 484 | 1 | GOILOC-128(P-3) | GOILOC-128 | supply, installation and maintenance of 30 paddy processing units.: Eligible Contract value USD 13,200,000.00 [CFR]
181 | 485 | 1 | GOILOC-129(P-1) | GOILOC-129 | Design and construction of the Medawachchiya to Madhu Road Railway Line in Sri Lanka
182 | 486 | 1 | GOILOC-129(P-2) | GOILOC-129 | Construction of the Madhu Road to Talai Mannar Railway Line in Sri Lanka
183 | 487 | 1 | GOILOC-129(P-3) | GOILOC-129 | Design and reconstruction of the Omanthai to Pallai Railway Line in Sri Lanka
184 | 488 | 1 | GOILOC-130(P-1) | GOILOC-130 | Potable water project (USD 4.896 mn)
185 | 489 | 1 | GOILOC-130(P-2) | GOILOC-130 | P Milk Processing Plant (USD 11.30 mn)
186 | 490 | 1 | GOILOC-132(P-1) | GOILOC-132 | Supply of electrical materials and construction of electric lines in 26 rural localities in the departments of Alibori, Atacora, Borgou and Donga
187 | 491 | 1 | GOILOC-132(P-2) | GOILOC-132 | Supply and installation of Solar Stree Light in Sierra Leone
188 | 492 | 1 | GOILOC-132(P-3) | GOILOC-132 | Acquisition of sixty (60) urban transport buses of 70 passengers (30 seats + 39 standees + 1 driver seat), twelve (12) complete engines, spare parts, equipment of workshops and training of mechanics
189 | 493 | 1 | GOILOC-132(P-4) | GOILOC-132 | Study, supply, service and works of installation of 225 KV line Boundiali-Ferkessedougou with creation of substation at Boundiali and extension of 225 KV substation at Ferkessedougou
190 | 494 | 1 | GOILOC-133(P-1) | GOILOC-133 | 600 TPD Ali Sabieh Cement Plant Project , Phase II
191 | 495 | 1 | GOILOC-134(P-1) | GOILOC-134 | [i] Procurement of 300 Double Decker Buses with 10% spare parts, equipment and related services [USD 24.58 million]; [ii] Procurement of 100 Single Decker Buses with 10% spare parts, equipment and related services [USD 6.09 million]; [iii] Procurement of 50 Articulated Buses with 20% spare parts, equipment and related services [USD 6.12 million]:
192 | 496 | 1 | GOILOC-134(P-2) | GOILOC-134 | Supply of 50 nos. MG flat wagons [BFCT] and 5 nos. MG Brake vans with Air Brake for carrying container
193 | 497 | 1 | GOILOC-134(P-3) | GOILOC-134 | Supply of 165 nos. BG bogie oil tank wagons and 6 nos. bogie brake vans to Bangladesh Railway
194 | 498 | 1 | GOILOC-134(P-4) | GOILOC-134 | Supply of 16 nos. Broad Guage [BG] Diesel Electric Locomotives
195 | 499 | 1 | GOILOC-134(P-5) | GOILOC-134 | Supply of 10 nos. Broad Gauge [BG] Diesel Electric Locomotives
196 | 500 | 1 | GOILOC-134(P-6) | GOILOC-134 | Supply of 81 nos. MG bogie tank wagons and 3 nos. MG Brake vans with air brake equipment for carrying aviation fuel
197 | 501 | 1 | GOILOC-134(P-7) | GOILOC-134 | Supply of 170 nos. MG flat wagons [BFCT] and 11 nos. MG Brake vans with Air Brake for carrying container
198 | 502 | 1 | GOILOC-134(P-8) | GOILOC-134 | Supply of 1 No. 18”/450 mm dia cutter suction dredger
199 | 503 | 1 | GOILOC-134(P-9) | GOILOC-134 | 120 Nos. BG Passenger Carriages, Capital Spares, Maintance spares and tools with related services
200 | 504 | 1 | GOILOC-134(P-10) | GOILOC-134 | 1. For conducting Detailed Feasibility Study, Detailed Design & Preparing Tender Documents; and Construction supervision services. 2. For construction of 2nd Bhairab railway bridge with approach rail lines and related works [Lot-A] 3. For construction of 2nd Titas railway bridge with approach rail lines and related works [Lot-B]
201 | 505 | 1 | GOILOC-134(P-11) | GOILOC-134 | Design, supply, installation, testing and commissioning of computer based interlocking colour light signaling system with works and services in three stations of Ashuganj-Akhaura section of East Zone of Bangladesh Railway
202 | 506 | 1 | GOILOC-134(P-12) | GOILOC-134 | Supply of 136 types of laboratory equipments, 200 types of chemicals, 160 types of glassware and related services
203 | 507 | 1 | GOILOC-134(P-13) | GOILOC-134 | 1. Consultancy services for Detailed feasibility study and safeguard policy study, Detailed engineering design and bidding services, and Construction supervision services 2. Construction of Railway bridge over the river Rushpa and implementation of EMP for the construction of Khulna-Mongla port rail line project 3. Construction of embankment, track, all civil works, major and minor bridges [except Rupsha Bridge] & culverts and implementation of environment management plan [Package WD1]
204 | 508 | 1 | GOILOC-134(P-14) | GOILOC-134 | 1. Consultancy services for detailed design & tendering services, construction supervision services 2. Construction of Railway track, embankment, bridge & culverts, station buildings, platforms & sheds and level crossings along with associated works in Dhaka-Tongi-Joydebpur section including supply of all labour, materials, equipment etc. in connection with Construction of 3rd and 4th Dual Guage tracks in Dhaka-Tongi section and Doubling of Dual Guage track in Tongi-Joydebpur section
205 | 509 | 1 | GOILOC-134(P-15) | GOILOC-134 | 1. Consultancy services for detailed design & tendering services and construction supervision services 2. EPC contract for the rehabilitation of Kulaura-Shahbazpur project
206 | 510 | 1 | GOILOC-135(P-1) | GOILOC-135 | Procurement of plant design, supply and Installation, testing & commissioning of Solu Corridor 132kV Double Circuit Transmission Line [Package KC1]
207 | 511 | 1 | GOILOC-135(P-2) | GOILOC-135 | Procurement of plant design, supply and Installation, testing & commissioning of Koshi Corridor (Inaruwa – Basantpur – Baneshwar – Tumlingtar) 220 kV Double Circuit Transmission Line
208 | 512 | 1 | GOILOC-135(P-3) | GOILOC-135 | Engineering, Procurement and Construction (EPC) Contract for the Civil Works and Design, Manufacture, Supply, Erection, Testing and Commissioning of Hydro Mechanical Works for “Rahughat Hydroelectric Project-40 MW”
209 | 513 | 1 | GOILOC-135(P-4) | GOILOC-135 | Procurement of Plant Design, Supply, Installation of (a) Laha Chowk 132 kV Substation, (b) New Modi 132 kV Switching Station and (c) 132 kV Line (partial, 2 bay expansion) at Lekhnath Substation
210 | 514 | 1 | GOILOC-135(P-5) | GOILOC-135 | Upgrading/improvement of roads viz. Ghorahi-Holeri section (31.5 km) of Sahid Marga [Ghorahi-Ghartigaun] Road
211 | 515 | 1 | GOILOC-135(P-6) | GOILOC-135 | Upgrading/improvement of roads viz. Bardaghat – Paldanda – Tribeni Road (12.50 Km)
212 | 516 | 1 | GOILOC-135(P-7) | GOILOC-135 | Upgrading/improvement of Devdaha-Tinau-Parsa section of Lumbinin Buddhist Road in Nepal (42 Km)
213 | 517 | 1 | GOILOC-135(P-8) | GOILOC-135 | Upgrading/ improvement of roads viz. Barjugad-Martadi Section of Sanfebagar-Martadi road in Nepal (27 Km)
214 | 518 | 1 | GOILOC-135(P-9) | GOILOC-135 | Upgrading/ improvement of roads viz. Balaju- Ranipauwa section of Balaju - Ranipauwa-Trisuli Road Road in Nepal (21.6 Km)
215 | 519 | 1 | GOILOC-135(P-10) | GOILOC-135 | Upgrading/ improvement of roads viz. Chahare-Bidur Road in Nepal (16.48 Km)
216 | 520 | 1 | GOILOC-135(P-11) | GOILOC-135 | Upgrading/ improvement of roads viz. Bhaktapur- Nagarkot section of [Bhaktapur –Nagarkot- Sipaghat] Road in Nepal (15.66 Km)
217 | 521 | 1 | GOILOC-135(P-12) | GOILOC-135 | Upgrading/ improvement of roads viz. Bharatpur – Chanauli section of Bharatpur – Rampur- Meghauli Road in Nepal (16 Km)
218 | 522 | 1 | GOILOC-135(P-13) | GOILOC-135 | Upgrading/ improvement of Jaleshor-Loharpatti section of Janakpur Parikrama road in Nepal (23 Km)
219 | 523 | 1 | GOILOC-135(P-14) | GOILOC-135 | Upgrading/ improvement of roads viz. Loharpatti-Mahendranagar Section of Janakpur Parikrama Road. (17 Km) [Allocation USD 3.70 mn]
220 | 524 | 1 | GOILOC-135(P-15) | GOILOC-135 | Upgrading/improvement of roads viz. Chovar-Dakchinkali Section of Balkhu-Dakchinkali Road (11.93 km)
221 | 525 | 1 | GOILOC-135(P-16) | GOILOC-135 | Upgrading/improvement of roads viz. Lamosangu-Mude Section of Lamosangu-Tamakoshi-Jiri Road (25 Km)
222 | 526 | 1 | GOILOC-135(P-17) | GOILOC-135 | Upgrading/improvement of roads viz. Matthigaun-Baidehi Section of Janakpur Parikrama Road (17.66 Km) [USD 3.80 mn]
223 | 527 | 1 | GOILOC-135(P-18) | GOILOC-135 | Upgrading/ improvement of roads viz. Ranipauwa - Trisuli of Balaju-Ranipauwa - Trisuli Road (34.09 Km) [USD 9.39 mn]
224 | 528 | 1 | GOILOC-135(P-19) | GOILOC-135 | Upgrading/ improvement of roads viz. Mahendranagar-Matthigaun Section of Janakpur Parikrama Road (17 Km)
225 | 529 | 1 | GOILOC-135(P-20) | GOILOC-135 | Upgrading of Janakpur Parikrama Road: Hanumannagar Chowk-Rampur-Bahurhwa-Akaura-Bhadiya, Jaleshwor-sungha-Matihanj-Tulsyahi-Baheda Bela and Railway station-Mills Area (9.5 Km) [Incl. Railway Station - Milsetiya section (3 km) of Janakpur Parikrama Road and Jaleshwor – Sungha- Matihani-Tulsiahi Baheda Bela section (11.48 km) of Janakpur Parikrama Road]
226 | 530 | 1 | GOILOC-135(P-21) | GOILOC-135 | Upgrading/ improvement of roads viz. Mude-Charikot Section of Lamosanghu-Tamakoshi-Jiri Road [USD 8.73 mn]
227 | 531 | 1 | GOILOC-136(P-1) | GOILOC-136 | Rural Electrification of Cabo Delgado, Manica, Niassa Provinces
228 | 532 | 1 | GOILOC-137(P-1) | GOILOC-137 | Detail, Design, Engineering and Construction of (9.3 MW Production) Kakobola Hydroelectric Power Project
229 | 533 | 1 | GOILOC-138(P-1) | GOILOC-138 | Reconstruction of the Pallai-Kankesanthurai Railway Line
230 | 534 | 1 | GOILOC-138(P-2) | GOILOC-138 | Design, supply, installation, testing and commissioning of signaling and telecommunication system for railway network in Northern and Talaimannar railway lines in Sri Lanka
231 | 535 | 1 | GOILOC-138(P-3) | GOILOC-138 | Supply of 326 Engine Kits for buses
232 | 536 | 1 | GOILOC-138(P-4) | GOILOC-138 | Supply of 10 Diesel Locomotives Railways
233 | 537 | 1 | GOILOC-138(P-5) | GOILOC-138 | Supply of 6 Diesel Multiple Units with Air Conditioned Passenger Compartments [2 AC compartment per DMU] Railways
234 | 538 | 1 | GOILOC-138(P-6) | GOILOC-138 | Supply of 163 Engine Kits for buses
235 | 539 | 1 | GOILOC-138(P-7) | GOILOC-138 | Supply of 20 container carrier wagons and 30 fuel tank wagons with braking systems.
236 | 540 | 1 | GOILOC-139(P-1) | GOILOC-139 | Completion of Stung Tasal Water Development Project | PQ process completed - Contract yet to be awarded |  | G-139 | Cambodia | 15 | Stung Tasal Water Resources Development Project, Phase-II | 10 | EPC | 2017-03-14 | 2017-04-13 |  | NA | NA | Pre-Qualified Companies List: i) JV of Om Metals Infra Projects Ltd and Navbharat Buildcon (P) Ltd. Contract Award: Yet to be awarded by GOC. Financial Negotiations are underway between the Pre Qualified JV and Government of Cambodia. Contract Inclusion form from GOC is awaited.
237 | 541 | 1 | GOILOC-140(P-1) | GOILOC-140 | Design, Supply, testing and commissioning of transmission line and substations
238 | 542 | 1 | GOILOC-141[P-1] | GOILOC-141 | Offshore Patrol Vessel from M/s Garden Reach Shipbuilders & Engineers Ltd
239 | 543 | 1 | GOILOC-142(P-1) | GOILOC-142 | Development of sugar industry
240 | 544 | 1 | GOILOC-143(P-1) | GOILOC-143 | (i) 230 kV Double Circuit Transmission Line from Nabong to Thabok and substations (USD 37.30mn), (ii) Improvement and Expansion of 22kV distribution line in Vientiane capital city branches project [USD 35.25 million] in Lao PDR
241 | 545 | 1 | GOILOC-144(P-1) | GOILOC-144 | Procurement of medical equipment and rehabilitation of health establishment in Benin | PQ process completed - Contract awarded |  | G144 (LOC to EBID) | Benin (LOC to EBID) | 150.00 (Project of USD 10 mn) | Procurement of medical equipment and rehabilitation of health equipment in Benin | 10 | SPPLY | 2016-08-26 | 2016-11-24 | 2018-06-25 | 2018-10-24 | 2018-11-13 | Pre-Qualified cos. List: Techfab Allengers Consortium has been prequalified for all the batches. Contract Award: Techfab Allengers Consortium on June 25, 2018.
242 | 546 | 1 | GOILOC-144(P-2) | GOILOC-144 | Rural Electrification Extension Project [Phase I of the project is included under the LOC of USD 250 million to EBID]
243 | 547 | 1 | GOILOC-144(P-3) | GOILOC-144 | Power Transmission Project Connecting Bamako and Sikasso via Bougouni in Mali [Part funding the project in Mali]
244 | 548 | 1 | GOILOC-144(P-4) | GOILOC-144 | Rural Electrification of 50 villages through Solar Photovoltaic (SPV) system in Niger | PQ process completed - Contract yet to be awarded |  | G144[4] (LOC to EBID) | Niger | 150.00 (Project of USD 10 mn) | Electrification of 50 Villages by Photovoltaic Solar System in Niger | 9.56 | EPC | 2017-11-09 | 2017-12-26 |  | NA | NA | Pre-Qualified Companies List: i) Jakson Engineers Ltd. ii) Sterling and Wilson Pvt. Ltd. iii) Waaree Energies Ltd. Contract Award: Yet to be awarded. Draft tender document approval has been conveyed to EBID on November 09, 2019. No bid were submiited by the pre-Qualified companies, EBID requested for re launch of PQ for which Letter dated 24.01.2020 was sent to MEA,seeking MEAs advice on the same .
245 | 549 | 1 | GOILOC-144(P-5) | GOILOC-144 | Upgradation of Electricity Distribution Capacity In Togo | PQ opened and under evaluation |  | G-144 (LOC to EBID) | Togo | 150 | Upgradation of Electricity Distribution Capacity In Togo | 10 | EPC | 2019-12-11 | 2020-01-27 |  | NA | NA | (i)Last date of submission of applications was 13-01- 2020 which got extended to 27 January 2020. (ii)Total 14 applications received , and are under evaluation.
246 | 550 | 1 | GOILOC-144(P-6) | GOILOC-144 | Rehabilitation and Extension of Electricity to the four regional capitals in Guinea | PQ to be Reinvited/Cancelled |  | G-144 (LOC to EBID) | Guinea | 150.00 (Project of USD 10.53 mn) | Rehabilitation and Extension of Electricity to the four regional capitals in Guinea | 0.26 | PMC | 2018-04-11 | 2018-05-14 |  | NA | NA | Pre-Qualified Companies List: i) REC Power Distribution Company Ltd. ii) Tata Power Delhi Distribution Ltd (Tata Power-DDL) iii) WAPCOS Ltd. Contract Award: PMC requirement has been cancelled by EBID. PQ for EPC is done .
247 | 551 | 1 | GOILOC-145(P-1) | GOILOC-145 | Supply of pea dehusking and splitting line, electric motors required for the pea dehusking and splitting line, electric hardware, switch gears, power cables, cable trays, etc. and spare parts. The scope of the work also comprised supervision of erection, commissioning of equipment including training
248 | 552 | 1 | GOILOC-146(P-1) | GOILOC-146 | Ketende Hydro-electric Project
249 | 553 | 1 | GOILOC-147(P-1) | GOILOC-147 | Enhancing productivity of rice, wheat, maize cultivation
250 | 554 | 1 | GOILOC-148(P-1) | GOILOC-148
251 | 555 | 1 | GOILOC-149(P-1) | GOILOC-149 | Setting up of Information Technology Park Project in Swaziland
252 | 556 | 1 | GOILOC-150(P-1) | GOILOC-150 | Development of sugar industry
253 | 557 | 1 | GOILOC-151(P-1) | GOILOC-151
254 | 558 | 1 | GOILOC-152(P-1) | GOILOC-152 | For installation of an 18 MW power project in Moroni, the capital city of Comoros
255 | 559 | 1 | GOILOC-153(P-1) | GOILOC-153 | Construction of Hydro Electric-Electric Project (20MW) in Burundi
256 | 560 | 1 | GOILOC-154(P-1) | GOILOC-154
257 | 561 | 1 | GOILOC-155(P-1) | GOILOC-155 | Milk powder Processing Plant in Camaguey Province of Cuba
258 | 562 | 1 | GOILOC-156(P-1) | GOILOC-156 | Rural Electrification Project
259 | 563 | 1 | GOILOC-157(P-1) | GOILOC-157 | Rural Electrification
260 | 564 | 1 | GOILOC-158(P-1) | GOILOC-158 | Solar Photo Voltaic Module Manufacturing Plant
261 | 565 | 1 | GOILOC-159(P-1) | GOILOC-159 | Design, Engineering, Manufacturing, Supply And Installation of Equipment, Operation and Transportation of Bobassa Limestone for Manufacturing of Cement
262 | 566 | 1 | GOILOC-160(P-1) | GOILOC-160 | Farming and cultivation of Rice, Maize and Sorghum in Togo
263 | 567 | 1 | GOILOC-161(P-1) | GOILOC-161 | Design, Engineering, Manufacture, Supply and Installation of Equipment, Machinery and Material for Extension of Baoli -2 Hydero Electric Power Project
264 | 568 | 1 | GOILOC-162(P-1) | GOILOC-162 | Extension of spinning mill extension of spinning mill (addition of weaving and processing capacities)
265 | 569 | 1 | GOILOC-163(P-1) | GOILOC-163
266 | 570 | 1 | GOILOC-164(P-1) | GOILOC-164 | Development of sugar industry
267 | 571 | 1 | GOILOC-165(P-1) | GOILOC-165 |  | PQ process completed - Contract yet to be awarded |  | G-165 | Cameroon | 42 | Cassava Plantation Project | 42 | SPPLY | 2017-08-22 | 2017-10-03 |  | NA | NA | Pre-Qualified Cos. List Lot – I: BEML Ltd. (BEML) Lot - II: TATA Motors Ltd. (TML) Lot - III: i) Escorts Ltd. (EL) ii) Mahindra & Mahindra Ltd. (M&M) iii) International Tractors Ltd. (ITL) iv) TAFE Ltd. (TAFE) Contract Award: GO-CMR issued letter of invitation for tender (Lot I, II and III ) to pre-qualified companies on 16.11.2018. Last date for bid submission was 04.03.2019 which was extended upto March 25,2019. Also a pre-bid meeting was sought by companies under Lot 1 and 2. GO-CMR had a pre-bid meeting on March 11 and March 12,2019 for Lot 1 and Lot 2 respectively. GO-CMR has provided clarification of the technical parameters and has extended the last date for bid submission to April 15, 2019. Pre-qualified companies under lot 3 have sought some more information on technical parameters and change in payment terms. GO-CMR issued addendum on April 24,2019 and extended the last date to May 15,2019 and also changed the payment terms. Bids submitted by BEML Ltd., TATA Motors Ltd. and TAFE Ltd. are under evaluation. Go-CMR has invited the bidders for negotiations during January 14- January 16, 2020. Bid Evaluation Report from GO-CMR is awaited.
268 | 572 | 1 | GOILOC-166(P-1) | GOILOC-166 | Design, build, equip, test, deliver, install, complete and commissioning of certain facilities viz. surgical specialty hospital, located at Turkeyen, Georgetown, Guyana.
269 | 573 | 1 | GOILOC-167(P-1) | GOILOC-167 | Pre-fabricated health posts
270 | 574 | 1 | GOILOC-168(P-1) | GOILOC-168 | Project Management Consultancy (PMC) Services for ensuring food security through increased maize production by soil conditioning, farm mechanization and granular fertilizer application, in Swaziland
271 | 575 | 1 | GOILOC-168(P-2) | GOILOC-168 | Project on ensuring food security through increased maize production by soil conditioning, farm mechanization and granular fertilizer application in Swaziland
272 | 576 | 1 | GOILOC-169(P-1) | GOILOC-169 | Power Transmission Project Connecting Bamako and Sikasso via Bougouni | PQ process completed - Contract awarded |  | G-169 | Mali | 100 | Power transmission project connecting Bamako and Sikasso via Bougouni in Mali | 145.18 | EPC | 2016-10-14 | 2016-11-22 | 2018-05-12 |  | KPTL -02/12/2019 Tata Projects - 01/03/2019 | Project Cost - 145.18, Funded under LOCs of USD 100 mn to Mali and USD 50 mn out of LOC of USD 150 mn to EBID. Pre-Qualified cos. List: i) Associated Power Structures Private Limited – Ketan Construction Limited JV (Package I), ii) EMC Limited (Package I), iii) Kalpataru Power Transmission Limited (Package I & III), iv) Bajaj Electricals Limited (Package I & III), v) KEC International Limited (Package I, II & III), vi) Larsen & Toubro Limited (Package I, II & III), vii) Megha Engineering & Infrastructure Limited (Package I &II), viii) Mohan Energy Corporation Private Limited (Package III), ix) Power Grid Corporation of India Limited (Package I & II), x) Sterling & Wilson Private Limited (Package III), xi) Tata Projects Limited (Package I, II & III), xii) Techno Electric & Engineering Company Limited (Package II). Contract Award: KPTL (package-¦) Tata Projects Limited (Package II) Mohan Energy Corporation Private Limited (Package III). KPTL - 19/09/2019 Tata Projects - 12/05/2018
273 | 577 | 1 | GOILOC-170(P-1) | GOILOC-170 | Low cost housing and economical buildings project in Burkina Faso
274 | 578 | 1 | GOILOC-171(P-1) | GOILOC-171 | Improving the quality of power supply in Mozambique
275 | 579 | 1 | GOILOC-172(P-1) | GOILOC-172 | Execution on Turnkey basis of 19 Cold Storage Complexes for preservation, freezing and storage of fish, fruits, vegetables.
276 | 580 | 1 | GOILOC-173(P-1) | GOILOC-173 | NA
277 | 581 | 1 | GOILOC-174(P-1) | GOILOC-174 | Sugar Plant project
278 | 582 | 1 | GOILOC-175(P-1) | GOILOC-175 | Pharmaceutical manufacturing plant
279 | 583 | 1 | GOILOC-176(P-1) | GOILOC-176 | Augmentation of water supply schemes of Dar es Salaam and Chalinze regions in Tanzania
280 | 584 | 1 | GOILOC-177(P-1) | GOILOC-177 | (a) development of irrigation network under greenbelt initiative; (b) setting up of refined sugar processing equipment in Salima under greenbelt initiative; and (c) development of fuel storage facilities in Malawi
281 | 585 | 1 | GOILOC-178(P-1) | GOILOC-178 | Construction of the National Assembly Building in Gambia
282 | 586 | 1 | GOILOC-178(P-2) | GOILOC-178 | Construction of the National Assembly Building in Gambia
283 | 587 | 1 | GOILOC-178(P-3) | GOILOC-178 | Construction of the National Assembly Building in Gambia : Package 1(A) and 1 (B)
284 | 588 | 1 | GOILOC-178(P-4) | GOILOC-178 | Construction of the National Assembly Building in Gambia
285 | 589 | 1 | GOILOC-178(P-5) | GOILOC-178 | Supply and installation of furniture and equipment under National Assembly Building Complex project in Gambia
286 | 590 | 1 | GOILOC-178(P-6) | GOILOC-178 | Design and works supervision under the National Assembly Building Complex Project in Gambia
287 | 591 | 1 | GOILOC-179(P-1) | GOILOC-179 | Tractor assembly plant and farm equipment manufacturing unit
288 | 592 | 1 | GOILOC-181(P-1) | GOILOC-181 | Up-gradation of Deka pumping station and river water intake system in Zimbabwe | PQ process completed - Contract yet to be awarded |  | G-181 G-297 | Zimbabwe | 48.1 | Up-gradation of Deka pumping station and river water intake system in Zimbabwe | 35.53 | EPC | 2019-10-01 | 2019-11-15 |  | NA | NA | 1. As the account of Technofab Engineering Ltd [TEL] has been categorised as NPA by 3 Indian Banks, Zimbabwe Power Corporation[ZPC] has cancelled the contract signed with TEL and requested for undertaking a fresh pre-qualification process for the said project. 2. The PQ document inviting fresh applications has been uploaded on Bank's website on October 1, 2019. The last date for submission of the PQ application was extended till November 15, 2019. Exim Bank has completed evaluation of 6 application received in the PQ process. Exim Bank on January 13, 2020 has forwarded the name of the single company pre-qualified in the evalaution process to GOZ. Name of Pre-qualified Company: Afcons Infrastructure Ltd- Vijeta Projects and Infrastructure Ltd [JV].
289 | 593 | 1 | GOILOC-182(P-1) | GOILOC-182 | Rural drinking water project extension
290 | 594 | 1 | GOILOC-183(P-1) | GOILOC-183 | Bulk Blending Fertilizer Plant in Cuba
291 | 595 | 1 | GOILOC-185(P-1) | GOILOC-185 | Mashkour Sugar Project (IInd tranche of US $ 150 mn)
292 | 596 | 1 | GOILOC-186(P-1) | GOILOC-186 | Farm Mechanization
293 | 597 | 1 | GOILOC-187(P-1) | GOILOC-187 |  | PQ process completed - Contract awarded |  | G-187 | Senegal | 41.96 | Setting up a Modern Abattoir, Meat Processing, Cold Storage, Rendering and Tannery Plant and Market Place in Senegal | 2.1 | PMC | 2016-10-21 | 2016-11-21 | 2017-08-31 |  | 2017-10-17 | Contract Award: G.K Sen & Associates on 31.08.2017
294 | 598 | 1 | GOILOC-188(P-1) | GOILOC-188 | Integrated Food Processing Complex in Burundi
295 | 599 | 1 | GOILOC-189(P-1) | GOILOC-189 | Rehabiliation of Road b/w Tica Buzi and Nova Sofala in Mozambique | PQ process completed - Contract awarded |  | G-189 | Mozambique | 149.72 | Rehabilitation of Road between Tica, Buzi and Nova Sofala in Mozambique | 149.72 | CC | 2017-05-25 | 2017-07-03 | 2018-03-30 | 2018-04-12 | 21-06.2018 | Pre-Qualified Cos. List: i) JMC Projects (India) Ltd. ii) Larsen & Toubro Ltd. iii) AFCONS Infrastructure Ltd. iv) IL&FS Transportation Networks Ltd. v) JV of Ashoka Buildcon Ltd. and GKC Project Ltd. Contract Award: Afcons Infrastructure Ltd. on 30.03.2018.The review meeting of the project was conducted on November 05, 2019 and the next review meeting has been scheduled on Jan 09, 2020. So far 13% financial progress and 13.5% physical progress has been achieved as per certification of Wapcos Ltd. [PMC]. Afcons informed on 30.12.2019 that opening of LC is under process and requested to schedule next review meeting between Jan 13-15, 2020. Second Review meeting held on Jan 20, 2020.
296 | 600 | 1 | GOILOC-190(P-1) | GOILOC-190
297 | 601 | 1 | GOILOC-191(P-1) | GOILOC-191 | Supply of Sub-station products
298 | 602 | 1 | GOILOC-192(P-1) | GOILOC-192 | Up gradation of sugar industry in Fiji
299 | 603 | 1 | GOILOC-193(P-1) | GOILOC-193 | Development of sugar industry
300 | 604 | 1 | GOILOC-194(P-1) | GOILOC-194 | 1) USD 16 mn [Dornier Aircraft supply] 2) USD 6 mn [Fast interceptor boats] 3) USD 7.75 mn [upgradation of Dornier Aircraft]
301 | 605 | 1 | GOILOC-195(P-1) | GOILOC-195 | Rehabilitation and Extension of forty-seven (47) Water Supply schemes in rural areas of Benin | PQ to be Reinvited/Cancelled |  | G-195 | Benin | 42.61 | Contractor for Construction, Rehabilitation and Extension of forty-seven Water Supply schemes in rural areas of Benin | 39.28 | EPC | 2018-03-13 | 2018-04-27 |  | NA | NA | Pre-Qualified Companies List: 1)Jain Irrigation Systems Ltd (JISL); 2) Technofab Engineering Ltd (TEL); Contract Award: Bid Documents have been issued to the pre-qualified companies by Government of Benin. Bid opening has been further extended till March13, 2019 from February 07, 2019 from earlier January 2019. Bid opening was done on March 13, 2019. Bid evaluation report from the project authority has been received. Exim Bank has conveyed no objection on the bid evaluation report on May 02, 2019. However, as the account of Technofab has been categorised as SMA by 3 indian Banks, Exim Bank on June 28, 2019 has suggested MEA-DPA to convey to GOB to undertake fresh pre-qualification process for drinking water supply systems in 69 villages in Benin. MEA-DPA's advice is awaited. MEA-DPA vide email dated July 11, 2019 approved to convey that GO-BEN may be advised to undertake fresh pre-qualification process for the said project. However, GO-BEN vide letter no. 935/2019/SASC/DM/DG/CAA dated July 26, 2019 has requested for evaluation of bid of JISL in order to avoid delay in commencement of the project resulting from fresh pre-qualification. MEA-DPA's advice has been sought on August 1, 2019. MEA-DPA's advise on the matter is awaited. Exim Bank on September 18, 2019 had sent a mail to GO-BEN seeking confirmation from GO-BEN whether evaluation and reconsideration of rejected bid of JISL is as per the prescribed Procurement Laws and does not involve any legal implications from the procedural point of view in future. GO-Ben vide its mail dated September 24, 2019 informed that it will have not have any objection to this decision as long as it is in line with the wish of the technical and financial partner. In response Exim Bank has asked GO-BEN to confirm no-objection received from relevant Procurement & legal authorities of GO-BEN unconditional to Exim Bank's response vide our letter dated October 04, 2019. GO-BEN vide letter ref. 360C/2019/SASF/DM/DG/CAA dated November 07, 2019 had confirmed that ARMP has conveyed it’s no objection to proceed with JISL. However, Exim Bank on November 18, 2019 advisedGO-BEN to undertake a fresh pre-qualification process for the captioned project as JISL has been categorized as NPA by its Banks. Reminder mail was again sent on December 20, 2019 seeking response on undertaking fresh pre-qualification process for the captioned project. The response from Government of Benin is awaited.
302 | 606 | 1 | GOILOC-197(P-1) | GOILOC-197 | Construction of 900 houses in Mozambique | PQ process completed - Contract yet to be awarded |  | G-197 | Mozambique | 47 | Construction of 900 houses in Mozambique | 33.38 | EPC | 2017-10-31 | 2017-12-15 |  | NA | NA | Pre-Qualified Companies List: i) IRCON International Ltd. ii) NBCC (India) Ltd. iii) Shapoorji Pallonji and Company Pvt. Ltd. Contract Award: Yet to be awarded. Tender issued to bidders on October 31, 2018. Retendering under progress due to change in tender model by FFH. Last date of bid submission was 28.05.2019. Bid Evaluation Report is awaited from FFH.
303 | 607 | 1 | GOILOC-198(P-1) | GOILOC-198 | Solar electrification of 30 villages and solar photovoltaic system of 5 MW
304 | 608 | 1 | GOILOC-199(P-1) | GOILOC-199 | Preparation of DPR for an Integrated Food Processing Complex (USD 38.16 mn) in Burundi
305 | 609 | 1 | GOILOC-200(P-1) | GOILOC-200 | Modernization of an Injectable products plant in Havana | PQ process completed - Contract awarded |  | G-200 | Cuba | 5.0492 | For financing the modernisation of an injectable products plant in Havana | 5.04 | EPC | 2017-01-31 | 2017-03-01 | 2018-04-29 | 2018-05-14 | 2018-06-25 | Pre-Qualified Companies List: i) Fabtech Technologies International Limited Contract Award: Fabtech Technologies International Limited on 25.06.2018
306 | 610 | 1 | GOILOC-201(P-3) | GOILOC-201 | [i] Modern Irrigated Agricultural Project; and [ii] Modern Irrigated Agricultural |  |  | G-201 | Rwanda | 120.05 | [i] Export Targeted Modern Irrigated Agricultural Project (USD 60.22 million); and [ii] Extension of Export Targeted Modern Irrigated Agricultural Project (USD 59.83 million): Tomato Processing plant | 11.22 | EPC | 2016-12-16 | 2017-01-16 |  | NA | NA | Pre-Qualified cos. List: i) SSP Pvt. Ltd ii) Seftech India Pvt. Ltd. Contract Award: Provisionally awarded to Seftech India Pvt. Ltd. by RAB. i) Exim Bank has written to RAB on 03.04.18 to justify the high increase in the cost of the project as compared to the DPR. ii) RAB vide letter dated June 14, 2018 advised the higher cost is on account of inclusion of certain significant machineries which were missing from the Bills of Quantities. Seftech has advised various revision in scope of project to reduce the cost, which is being analysed by RAB and Wapcos. iii) Govt. of Rwanda along with Wapcos has negotiated the contract price with Seftech and arrived at USD 14.98 mn. iv) Exim Bank on November 15, 2018 has requested RAB to review the technical evaluation and consider seeking revised bids from the bidders on basis of revised BOQ. RAB on February 07, 2019 has conveyed that Exim Bank’s advice of seeking the revised bids from the bidders on basis of revised BOQ is not acceptable in terms of their prevailing procurement laws and regulations. RAB has requested for award of the contract of USD 14.98 mn to Seftech Ltd. Matter referred to MEA. v) The decision of Govt. of India to to cancel the current process and undertake a fresh tender process has been conveyed to RAB on June 7, 2019. RAB was to request to get the DPR revalidated on basis of the revised scope of work and current prices to enable Exim Bank to undertake the pre-qualification process based on revalidated DPR. Response of GO-RWA is awaited. RAB on February 11, 2010, advised the cancellation of Tomato Processing plant and Maize processing plant, requesting for utilisation of the funds of the Tomato processing project and Maize processing plant to increase irrigation area under the LOC. Exim Bank referred the matter to MEA for consideration on February 27, 2020.
307 | 611 | 1 | GOILOC-202(P-1) | GOILOC-202 | Stung Sva Hab/Slab Water Resources Development Project
308 | 612 | 1 | GOILOC-203(P-1) | GOILOC-203 | Construction of Nam Nga Dam Project and Nam Xang Project in Lao PDR | PQ document under preparation |  | G-203 | Lao PDR | 30.94 | Construction of Nam Xang Project in Lao PDR | 20.49 | EPC |  |  |  | NA | NA | Re-PQ (3rd PQ exercise) i) One application received in 1st PQ exercise; Om Metals Infraprojects Ltd. However, the applicant failed to qualify. ii) Two application received in 2nd PQ exercise: Avantika Contractors (I) Ltd. and Bekem Infra Projects Ltd. [Avantika-Bekem JV]; and Om Metals Infra Projects Ltd and SPML Limited [Om-SPML JV]. OM-SPML was Pre-qualified. However, before the contract was awarded, SPML was classified as ‘Sub-standard’ in CRILC. iii) On November 20, 2019, MEA advised Exim Bank to conduct fresh PQ for construction of Nam Xang Dam dam. iv) Exim Bank on December 12, 2019 has sent the draft PQ document for construction of Nam Xang Dam in Xayabury province to Indian Mission. Awaiting GO-LAO's inputs on the revised PQ document.
309 | 613 | 1 | GOILOC-204(P-1) | GOILOC-204 | Development of Agriculture and Irrigation Infrastructure in the Jamastran Valley in Honduras
310 | 614 | 1 | GOILOC-205(P-1) | GOILOC-205 | Preparation of Detailed Project Report (DPR) for Power Transmission and Distribution Project | PQ to be Reinvited/Cancelled |  | G-205 | Liberia | 144 | Power Transmission and Distribution Project |  | PMC | 2016-05-09 | 2016-06-08 |  | NA | NA | PQ was cancelled by the borrower.
311 | 615 | 1 | GOILOC-206(P-1) | GOILOC-206 | Capitalization of Interest under operative LOCs for change in terms of the existing LOCs
312 | 616 | 1 | GOILOC-207(P-1) | GOILOC-207 | Land and Infrastructure Development including Hydarulics, Water Management System (Irrigation) and Provision of Tractors.
313 | 617 | 1 | GOILOC-208(P-1) | GOILOC-208 | Procurement of 12 units of D 155 bulldozers including spare parts
314 | 618 | 1 | GOILOC-209(P-1) | GOILOC-209 | 600 TPD Ali Sabieh Cement Plant Project , Phase II
315 | 619 | 1 | GOILOC-210(P-1) | GOILOC-210 | Expansion of the ongoing projects for rehabilitation of existing potable water facilities in four communities in Sierra Leone
316 | 620 | 1 | GOILOC-211(P-1) | GOILOC-211 | Potable Water for Semi-Urban and Rural Communities
317 | 621 | 1 | GOILOC-212(P-1) | GOILOC-212 | Development of Transport System
318 | 622 | 1 | GOILOC-213(P-1) | GOILOC-213 | To finance the acquisition of Waterjet Fast Attack Craft
319 | 623 | 1 | GOILOC-214(P-1) | GOILOC-214
320 | 624 | 1 | GOILOC-215(P-1) | GOILOC-215 | Procurement and Construction (EPC) Contractors for Construction and Establishment of 130 Bedded Mother & Child Hospitals at Kankan and N’Zerekore, Republic of Guinea | PQ process completed - Contract yet to be awarded |  | G-215 | Guinea | 35 | Contractors for Construction and Establishment of 130 Bedded Mother & Child Hospitals at Kankan and N’Zerekore, Republic of Guinea, Africa | 34 | EPC | 2018-05-25 | 2018-07-10 |  | NA | NA | Pre-Qualified Companies List: i) Ircon International Ltd. ii) JMC Projects (India) Ltd. iii) Shapoorji Pallonji & Company Pvt. Ltd. Contract Award: Exim Bank's observation on Bid Evaluation Report Submitted to MEA on 16.10.2019 and 27.12.2019.MEA's response awaited.
321 | 625 | 1 | GOILOC-216(P-1) | GOILOC-216 | Rural Electrification Project to cover 150 localities | PQ process completed - Contract awarded |  | G-216 | Togo | 30 | Rural Electrification Project to cover 150 localities | 28.52 | EPC | 2017-06-12 | 2017-07-12 | 2018-05-24 | 2018-08-03 | 2018-09-20 | Pre-Qualified cos. List: i) Bajaj Electricals Ltd. ii) Kalpataru Power Transmission Ltd. iii) KEC International Ltd. iv) KEI International Ltd. v) JV of MBH Power Private Limited & Shreem Electrical Limited vi) Shirdi Sai Electricals Ltd. vii) Shyama Power India Ltd. viii) SkipperSeil Ltd. ix) Sterling & Wilson Pvt Ltd. x) TATA Projects Ltd. xi) Technofab Engineering Ltd. Contract Award: Contracts awarded on 24.05.2018. Lot 1: Bajaj Electricals Ltd. Lot 2: Sterling & Wilson Pvt Ltd. Lot 3: SkipperSeil Ltd.
322 | 626 | 1 | GOILOC-217(P-1) | GOILOC-217 | Construction of 161kv Power Transmission Line Line linking Kara-Mango-Dapaong-Mandouri and Associated Substations in Togo Associated Substations in Togo | PQ process completed - Contract yet to be awarded |  | G-217 | Togo | 52 | Setting up of 161 KV Power Transmission Line | 58.03 | EPC | 2018-06-25 | 2018-08-08 |  | NA | NA | Project Cost - 58.03, There is a shortfall between the project cost and LOC value. The funding arrangement is to be decided by GOT subsequent to tendering process for EPC contractor Pre-Qualified Companies List: i) Bajaj Electricals Ltd. (Package I) ii) Kalpataru Power Transmission Ltd. (Package I) iv) KEC International Ltd. (Package I and II) v) Larsen & Toubro Ltd. (Package I and II) vi) Mohan Energy Corp JV Associated Power Structures P. Ltd. (Package I) viii) Shreem Electric Ltd. (Package II) ix) Shyama Power India Ltd. (Package I and II) x) Simplex Infrastructures Ltd. (Package I) xi) Techno Electric & Engineering Co. Ltd. (Package II) xii) Transrail Lighting Ltd. (Package I) Contract Award: The list of PQcompanies was advised to GOT on 03.10.2018. Pre-qualification of EMC Ltd and RS Infraprojects Pvt. Ltd. JV Ketan Constructions Ltd. has been cancelled as they have been declared sub-standard by their Banks as is seen in the RBI CRILIC Report. Revised list of pre-qualified companies along with reviewed tender document was sent to GOT on 15.2.2019. Final tender document has been released to the pre-qualified bidders on15.3.2019. Last date for bid submission was extended to July 02, 2019 by CEB based on the request of bidders. Bid evalution was received on August 12, 2019 for Exim Bank's review. Bid evalution report was received and Exim Bank conveyed no-objection on the evaluation report on August 22, 2019. Draft contract agreements have been received on December 30, 2019 and the go ahead has been conveyed to CEB on January 3, 2020. Letter dated February 14, 2020 has been sent to MEA seeking their go-ahead for inclusion of the PMC contract of WAPCOS Ltd.
323 | 627 | 1 | GOILOC-218(P-1) | GOILOC-218 | Design, Engineering and Construction of Grand Katende Hydro Electric Power Project
324 | 628 | 1 | GOILOC-219(P-1) | GOILOC-219 | Consultancy services for design, tendering and supervision of the project viz. replacement of Asbestos Water Pipes with UPVC Pipes in the Greater Banjul area in Gambia | PQ process completed - Contract awarded |  | G-219 | Gambia | 22.5 | Water Pipeline Replacement Project | 22.5 | EPC | 2016-11-25 | 2017-01-02 | 2018-04-05 | 2018-05-15 | 2018-08-20 | Pre-Qualified cos. List: i) Jain irrigation Systems Ltd ii) Shapoorji Pallonji & Company Pvt Ltd and SMC Infrastructure Pvt Ltd - JV iii) Technofab Engineering Ltd Contract Award: SPCPL - SMCIPL JV on April 05, 2018
325 | 629 | 1 | GOILOC-219(P-2) | GOILOC-219 | Project for replacement of Asbestos Water Pipes with uPVC Pipes in the Greater Banjul area of the Gambia
326 | 630 | 1 | GOILOC-220(P-1) | GOILOC-220 | Sugarcane development and irrigation project
327 | 631 | 1 | GOILOC-221(P-1) | GOILOC-221 | Tranmission Line and Sub-station | PQ process completed - Contract awarded |  | G-221 | Nicaragua | 26.24 | Supply for building Carlos Fonseca Substation, 95 Km Transmission Lines and expansion of three Substations (Villa El Carmen, Las Colinas & San Rafael del Sur) in Nicaragua | 26.24 | EPC | 2017-02-22 | 2017-04-07 | 2018-09-07 | - | 2018-11-20 | Pre-Qualified Companies List: i) EMC Ltd. ii) KEC International Ltd. iii) L & T Ltd iv) MEC-APSL JV v) PGCIL vi) Shyama Power India Ltd. Contract Award: KEC International Ltd. on September 07, 2018.
328 | 632 | 1 | GOILOC-222(P-1) | GOILOC-222
329 | 633 | 1 | GOILOC-223(P-1) | GOILOC-223 | Consultancy services for design, tendering and supervision of the Electrification Expansion Project for Greater Banjul Area in Gambia | PQ process completed - Contract awarded |  | G-223 | Gambia | 22.5 | Electricity Expansion Project | 22.5 | EPC | 2016-12-02 | 2017-01-02 | 2017-11-24 | 2018-01-08 | 2018-01-12 | Pre-Qualified cos. List: i) Bajaj Electricals Limited ii) KEC International Limited iii) KEI Industries Limited iv) Larsen & Toubro Limited v) Sterling & Wilson Private Limited vi) Technofab Engineering Limited Contract Award: KEI Industries Limited on November 24, 2017
330 | 634 | 1 | GOILOC-223(P-2) | GOILOC-223 | Electricity expansion work project in Greater Banjul area in the Gambia
331 | 635 | 1 | GOILOC-224(P-1) | GOILOC-224 | NA
332 | 636 | 1 | GOILOC-225(P-1) | GOILOC-225
333 | 637 | 1 | GOILOC-227(P-1) | GOILOC-227 | Upgrading/ improvement of roads viz. Charikot-Tamakoshi-Jiri sector of Lamosanghu-Tamakoshi-Jiri Road | PQ process completed - Contract yet to be awarded |  | G-227 | Nepal | 550 | Various road projects | 49.82 | CC | 2019-01-25 | 2019-11-03 |  |  |  | Pre-Qualfied Companies List: [i] Package III- Supreme-Swachchanda JV; ECI Engineering & Constructions; IL & FS Transportation Ltd; JMC Projects Ltd. Pre-Qualfied Companies List (after re-invitation in January 2019) : [i] Package III- Ashoka Buildcon Ltd., Telecommunication Consultants India Ltd., Woodhill-Lama JV. No Bid was received under Package III. DOR to re-invite PQ. DOR has requested for single stage two envelope for contracts where no bids were received. The matter was refered to MEA-DPA on November 9, 2018. MEA on 07.01.2019 advised to reinvite applications from the prequalified companies. Application document for reinvitation published on 25.01.2019. 14 Applications were received and were jointly evaluated on April 24-25, 2019 by Exim Bank and DOR-GON. Four Applicants were prequalified. MBL Infrastructure Ltd. has been excluded from list of pre-qualified companies due to its NPA status. GON has been informed that Woodhill-Lama JV was debarred by Government owned company viz. NHIDCL and hence be excluded from list of pre-qualified applicants. Tender document has been published by DOR on 20.02.2020.
334 | 638 | 1 | GOILOC-227(P-2) | GOILOC-227 | Upgrading/ improvement of roads viz. Kaligandaki Corridor, Gaidakot-Rampur-Pipaldanda Road | PQ process completed - Contract awarded |  | G-227 | Nepal | 550 | Various road projects | 91.71 | CC | 2017-09-18 | 2017-12-14 | 2018-11-19 | 2018-11-21 | Package I - 22-2.2019 Package II: 21.1.2019 Package III: 15.2.2019 | Pre-Qualfied Companies List: [i] Package I- APCO Infratech Pvt. Ltd; Gawar Constructions Ltd; AFCONS Infrastructures Ltd; KMC- Tundi JV; Dineshchandra-Kalika JV; JMC Projects Ltd. [ii] Package II- Supreme-Swachchanda JV; ECI Engineering & Constructions; IL & FS Transportation Ltd; JMC Projects Ltd. [iii] Package IV- IL & FS Transportation Ltd; AFCONS Infrastructures Ltd; JMC Projects Ltd; EKK Infrastructures Ltd. Contract Award: Package I- APCO Infratech Pvt. Ltd. Package II- Woodhill- Lama JV Package IV- EKK Infrastrutures Ltd.
335 | 639 | 1 | GOILOC-227(P-3) | GOILOC-227 | Upgrading/ improvement of Bhedetar-Ranke sector of Bhedetar-Rabi-Ranke Road | PQ process completed - Contract awarded |  | G-227 | Nepal | 550 | Various road projects | 210.63 | CC | 2017-09-18 | 2017-12-19 | 2018-05-12 | 18-12-2018 | Package VI : 6.3.2019 Package VII: 24.4.2019 Package VIII: 26.4.2019 | Pre-Qualfied Companies List: [i] Package VI- PRL-Kumar JV; IL & FS Transportation Ltd; Dinesh Chandra-Kanchanjunga JV; Woodhill-Lama JV; Gawar Constructions Ltd; JMC Projects Ltd. [i] Package VII- JMC Projects Ltd; Shivalaya-Diwa JV; IL & FS Transportation Ltd. [iii] Package VIII- Shivalaya- Mahalaxmi JV; DRAIPL SNMS JV; JMC Projects Ltd; Barbarik- ANK JV; IL & FS Transportation Ltd; AIPL-Raman JV. Contract Award: Package VI- PRL-Kumar JV Package VII- Shivalaya-Diwa JV Package VIII- DRAIPL SNMS JV Package VI: 5.12.2018 Package VII:5.12.2018 Package VIII:06-12-2018
336 | 640 | 1 | GOILOC-227(P-4) | GOILOC-227 | Upgrading/ improvement of Sahajpur-Gadebajh sector of Sahajpur-Boktan Road in Nepal - 50.027 km | PQ process completed - Contract awarded |  | G-227 | Nepal | 550 | Various road projects | 46.67 | CC | 2017-09-18 | 2017-12-19 | 2019-03-01 | 2019-03-07 | NA | Pre-Qualfied Companies List: [i] Package V- KMC-Tundi JV; IL & FS Transportation Ltd; JMC Projects Ltd; APCO Infratech Ltd; Gawar Constructions Ltd; R.K. Infracop Ltd; Dinesh Chandra Infracon Ltd. Contract Award: KMC-Tundi JV. However, contract has not been included under the LOC due to NPA status of KMC Constructions Limited(Indian JV partner) and the borrower has been advised accordingly. Borrower has issued a notice of termination to KMC Constructions in December 2019.
337 | 641 | 1 | GOILOC-227(P-5) | GOILOC-227 | Upgrading/ improvement of Jaleshwor, Rajbiraj and Siraha Urban Road in Nepal | PQ process completed - Contract awarded |  | G-227 | Nepal | 550 | Various road projects | 31.6 | CC | 2017-09-18 | 2017-12-19 | 2019-01-25 | Package IX: 29.1.2019 Package X: 29.1.2019 Package XI: 25.2.2019 Package XII: 29.1.2019 | Package IX: 12.7.2019 Package X: 21.5.2019 Package XI: 26.4.2019 Package XII: 21.5.2019 | Pre-Qualfied Companies List: [i] Package IX- Woodhill-Lama JV; Barbarik-ANK JV; AIPL-Raman JV; IL & FS Transportation Ltd; JMC Projects Ltd; KMC-Tundi JV; Gawar Constructions Ltd; Dinesh Chandra -Kalika JV ; APCO Infratech Pvt. Ltd. [ii] Package X- Woodhill-Lama JV; IL & FS Transportation Ltd; JMC Projects Ltd; Shivalaya-Diwa JV; KMC-Tundi JV; Gawar Constructions Ltd.; Dineshchandra-Kalika JV, APCO Infratech Pvt. Ltd.. [iii] Package XI- PRL-Kumar JV, IL & FS Transportation Ltd; JMC Projects Ltd, GHV-Hindung JV; Shivalaya-Diwa JV; KMC-Tundi JV; Gawar Constructions Ltd. Dineshchandra-Kalika JV, APCO Infratech PVt. Ltd. [iv] Package XII- IL & FS Transportation Ltd; JMC Projects Ltd, GHV-Hindung JV; Shivalaya-Diwa JV; RK Infracorp Pvt. Ltd, KMC-Tundi JV; Gawar Constructions Ltd. Dineshchandra-Kalika JV, Tathya Engineering & Infraproject Ltd, APCO Infratect Pvt. Ltd, Woodhill-Lama JV, PRL-Kumar JV, APIL-Raman JV, S&P Infrastructure Development Co. Contract Award: Package IX- Dineshchandra-Kalika JV Package X- Shivalaya-Diwa JV Package XI- PRL-Kumar JV Package XII- Tathya Engineering & Infraproject Ltd Package IX :25.1.2019 Package X: 29.12.2019 Package XI: 7.3.2019 Package XII: 28.12.2019
338 | 642 | 1 | GOILOC-227(P-6) | GOILOC-227 | Upgrading/Improvement of Basantapur-Kathariya-Kawahigoth-Pipardi-Padam Road and Malangawa Urban Road in Nepal
339 | 643 | 1 | GOILOC-227(P-7) | GOILOC-227 | Upgrading/ improvement of MRM-Gulariya-Rajanawa Roads and Nepalgunj Urban Road in Nepal - 51.03 km
340 | 644 | 1 | GOILOC-227(P-8) | GOILOC-227 | Upgradation/ Improvement of Gandak Canal Road in Nepal. - 61.91 km
341 | 645 | 1 | GOILOC-227(P-9) | GOILOC-227 | Upgrading/ improvement of Lamahi-Ghorahi-Tulsipur [Double Lane] Road in Nepal
342 | 646 | 1 | GOILOC-227(P-10) | GOILOC-227 | Upgradation/ Improvement of Chandaruta-Krishnanagar Road and Krishnanagar Urban road
343 | 647 | 1 | GOILOC-227(P-11) | GOILOC-227 | Bagdula-Bhimgitte Road
344 | 648 | 1 | GOILOC-227(P-12) | GOILOC-227 | Shelleghat-Ramechhap-Sangutar Road
345 | 649 | 1 | GOILOC-229(P-1) | GOILOC-229 | Study, Supply, Service and works of installation of the 225 KV Laboa-Boundiali Line and extension of sub-station at Laboa (Lot No. 1.2), Electricity Network Interconnection project between Côte d’Ivoire and Mali, valued at USD 8,640,000/-
346 | 650 | 1 | GOILOC-229(P-2) | GOILOC-229 | Study, Supply, Service and works of installation of the 225 KV Boundiali- Ferkessedougou Line with creation of sub-station at Boundiali and extension of 225 KV sub-station at Ferkessedougou (Lot No. 2.2), Electricity Network Interconnection project between Côte d’Ivoire and Mali, valued at USD 15,060,000/-
347 | 651 | 1 | GOILOC-230(P-1) | GOILOC-230 | Setting up a Greenfield 600 tpd rotary kiln Cement Plant Project | PQ process completed - Contract awarded |  | G-230 | R. Congo | 55 | Setting up a Greenfield 600 tpd rotary kiln Cement Plant Project | 55 | EPC | 2016-11-08 | 2016-12-08 | 2017-12-20 | 2018-03-05 | 2018-03-27 | Pre-Qualified cos. List Package I [Mining activities]:- Promac Engineering Industries Ltd. in consortium with Ercom Engineers Private Ltd. Package II [Cement Plant]: FLSmidth Private Ltd. and Promac Engineering Industries Ltd. Contract Award: Package I [Mining activities]:- Promac Engineering Industries Ltd. in consortium with Ercom Engineers Private Ltd. on December 20, 2017 Package II [Cement Plant]: Corrigendum document issued on August 5, 2019 to the 2 pre-qualified companies with last date of submission as September 10,2019. FLSmidth vide letter of August 16,2019 informed Embassy of R.Congo that they cannot participate at this time due to their organisational restructuring. Promac Engineering Industries Ltd is the sole bidder and a draft contract was shared yb GO-ROC with Exim Bank. Exim Bank conveyed its obsevation on the contract terms on December 18, 2019. Subseqneuty on January 16, 2020, GO-ROC has again forwarded to Exim Bank the revised payment terms.
348 | 652 | 1 | GOILOC-231(P-1) | GOILOC-231
349 | 653 | 1 | GOILOC-233(P-1) | GOILOC-233 | Power Distribution Project in Bandundu Province of D R Congo | PQ process completed - Contract awarded |  | G-233 | D.R.Congo | 34.5 | Development of Power Distribution Project in Bandundu Province of D. R. Congo | 34.5 | EPC | 2017-03-24 | 2017-04-25 | 2018-08-11 |  | 2018-10-26 | Pre-Qualified Cos. List: i) EMC Ltd ii) Kalpataru Transmission iii) KEC International iv) Mohan Energy & Associated Power Structures v) Shyama Power India Ltd. Contract Award: Mohan Energy & Associated Power Structures on 11.08.2018
350 | 654 | 1 | GOILOC-234(P-1) | GOILOC-234
351 | 655 | 1 | GOILOC-235(P-1) | GOILOC-235 | Rehabilitation and Up-gradation of Potable Water System in Yendi, Ghana | PQ process completed - Contract yet to be awarded |  | G-235 | Ghana | 30 | Rehabilitation and Up-gradation of Potable Water System in Yendi, Ghana | 30 | DPR+PMC | 2019-12-04 | 2020-01-20 |  | NA | NA | [i] Last date for submission extended from January 6, 2020 to January 20, 2020. [ii] Received 10 applications. Apart from Rudrabhishek Enterprises Ltd. all the other 9 appliants were Pre-qualified; WAPCOS Ltd., Shah Technical Consultants Pvt. Ltd., RITES Ltd., Royal HaskoningDHV Consulting Pvt. Ltd., TATA Consulting Engineers Ltd.,Crux Consultants Pvt. Ltd., DRA Consultants Ltd., Stup Consultants Pvt. Ltd., Aarvee Associates Architects Engineers & consultants Pvt. [iii] Exim Bank on February 14, 2020 has forwarded the name of the company pre-qualified in the evalaution process to GO-GHA.
352 | 656 | 1 | GOILOC-236(P-1) | GOILOC-236 | Strengthening of Agriculture Mechanization Service Centres in Ghana | PQ uploaded presently on website |  | G-236 | Ghana | 150 | Strengthening of Agriculture Mechanization Service Centres in Ghana | 150 | DPR+PMC | 2020-02-06 | 2020-03-09 |  | NA | NA | Re-PQ (2nd PQ exercise): 1) Two application received in first PQ exercise (PQ document published on Oct 2019); Mahindra Consulting Engineers Limited, and WAPCOS Ltd- Global Agrisystem Pvt. Ltd. JV. None of the applicants were pre qualified. 2) GO-GHA on January 31, 2020 advised to undertake fresh pre-qualification process for the project, with relaxed criteria.
353 | 657 | 1 | GOILOC-237(P-1) | GOILOC-237 | East Bank-East Coast Road linkage project
354 | 658 | 1 | GOILOC-238(P-1) | GOILOC-238 | Extension of Lake Victoria Pipeline to Tabora, Igunga and Nzega | PQ process completed - Contract awarded |  | G-238 | Tanzania | 268.35 | Extension of Lake Victoria Pipeline to Tabora, Igunga and Nzega | 251.3 | EPC | 2016-06-17 | 2016-08-08 | 2017-05-29 | 2017-06-19 | 2017-08-04 | Pre-Qualified Cos. List: Pre-Qualified Cos are: Package-I -Megha Engineering & Infrastructures Ltd.,Pratibha Industries Ltd.,JV of Afcons Infrastructure Ltd. & SMC Infrastructure Pvt. Ltd.,JV of L&T Constructions & Sriram EPC,JV of SPML Infra Ltd. & OM Metals Infraprojects Ltd.,JV of JMC Projects (India) Ltd. with Ramky Infrastructure Ltd. and Jain Irrigation Systems Ltd. Package-II-Megha Engineering & Infrastructures Ltd.,Pratibha Industries Ltd.,JV of Afcons Infrastructure Ltd. & SMC Infrastructure Pvt. Ltd.,JV of L&T Constructions & Sriram EPC and JV of SPML Infra Ltd. & OM Metals Infraprojects Ltd. Package-III-Megha Engineering & Infrastructures Ltd.,Pratibha Industries Ltd.,JV of Afcons Infrastructure Ltd. & SMC Infrastructure Pvt. Ltd.,JV of L&T Constructions & Sriram EPC,JV of SPML Infra Ltd. & OM Metals Infraprojects Ltd., and JV of JMC Projects (India) Ltd. with Ramky Infrastructure Ltd., Contract Award: Megha Engineering & Infrastructures Ltd., (package -I) on 29.05.2017 JV of L&T Constructions & Sriram EPC (Package-II) on 09.05.2017 JV of Afcons Infrastructure Ltd. & SMC Infrastructure Pvt. Ltd., (Package-III) on 29.05.2017
355 | 659 | 1 | GOILOC-239(P-1) | GOILOC-239
356 | 660 | 1 | GOILOC-240(P-7) | GOILOC-240 | Development of E-Health for Govt. of Mauritius
357 | 661 | 1 | GOILOC-241(P-1) | GOILOC-241
359 | 663 | 1 | GOILOC-243(P-1) | GOILOC-243 | As per discussion in a meeting at MEA on 08.02.2019, any further action in the project is linked to the developments in the Katende HEP Project financed under the LOCs of USD 168 mn and USD 82 mn.
360 | 664 | 1 | GOILOC-244(P-1) | GOILOC-244 | Tranmission Line and Sub-station | PQ process completed - Contract awarded |  | G-244 | Nicaragua | 31.29 | Transmission Line & Substation Project | 24.63 | EPC | 2018-05-18 | 2018-07-02 | 2020-01-28 | 2020-02-24 | Yet to be included | Pre-Qualified Cos. List 1. Bajaj Electricals Ltd. 2. Kalpataru Power Transmission Ltd. 3. KEC International Ltd. 4. Mohan Energy Corporation Pvt Ltd in JV with Associated Power Structure Ltd 5. Simplex Infrastructures Ltd 6. Shyama Power India Ltd. 7. RS Infraprojects Pvt Ltd in JV with Powertech Engineers 8. Transrail Lighting Ltd. Four companies have submitted the bid: 1. Kalpataru Power Transmission Ltd. 2. Transrail Lighting Ltd. 3. Shyama Power India Ltd. 4. KEC International Ltd. Contract Award: Transrail Lighting Ltd.
361 | 665 | 1 | GOILOC-245(P-1) | GOILOC-245

## Sheet4
SerialNo | ProjectID | More | ProjectCode | LOC NUMBER | Purpose | Category | Sr. no. | LOC Ref. No. | Country | LOC amount (USD million) | Project | Project Cost for which PQ is being /was undertaken (USD mn) | Category | PQ documents published on | Last date for submission | Date of Contract Signing | Date of receipt of Contract Agreement & Contract Inclusion Form by Exim Bank | Date of Contract Inclusion by Exim Bank | Status
381 | 140 | 2 | GOILOC-252(P-1) | GOILOC-252 | Transmission Line and Substation in Sierra Leone | PQ document under preparation |  | G-252 | Sierra Leone | 78 | 225 KV/66 KV/ 33 KV double/single circuit transmission lines and associated substations | 67.67 | EPC |  |  |  | NA | NA | The draft prequalification document sent to Government of Sierra Leone on November 13, 2019 for comments and information regarding the Equipment required and the Skilled Human Resources required for the project. Response of Govt. of Sierra Leone is awaited . Followup email sent on January 02, 2020 and February 05, 2020.
382 | 141 | 2 | GOILOC-253(P-1) | GOILOC-253 |  | PQ uploaded presently on website |  | G-253 | Mauritius | 46 | Acquisition of 12 Light Armoured Personnel Carriers (LAPCs) | 12 | SPPLY-DEFENCE | 2020-01-21 | 2020-03-06 |  | NA | NA | 1. MEA-DPA vide communication dated 06.06.2019 advised Exim Bank to undertake the pre-qualification process as GOM has cancelled all negotiations with BEML Ltd. for supply of LAPCs. 2. Exim Bank forwarded the draft PQ document to Mauritius Police Force on 19.01.2019. 3. On 27.08.2019, inputs on PQ document was forwarded by Mauritius Police Force [MPF] and sugggested Exim Bank to include specific technical parameters and requirements for shortlising the suppliers. The draft document was shared with MPF on 13.09.2019 for their concurrence. Specifications are reviewed by MPF. 4. On 20.01.2020, MPF conveyed over the telecon that there are no more modification in the LAPC's specification which can now be published. The PQ document was published on 21.01.2020. Last date of submission is March 6, 2020
394 | 153 | 2 | GOILOC-265(P-1) | GOILOC-265 | Setting up of a 50 MW Co-generation power plant in Cuba | PQ process completed - Contract yet to be awarded |  | G-265 | Cuba | 90.3 | 50 MW Co-generation Power Plant | 111.25 | EPC | 2018-11-13 | 2019-01-14 |  | NA | NA | Pre-Qualified Companies List: i) S.S.Engineers. ii) Five-Cail KCP Ltd. iii) Kay Bouvet Engineering Ltd. iv) ISGEC Heavy Engineering Ltd. v) Thyssenkrupp Industries India Pvt Ltd Contract Award: Yet to be awarded. Govt. of Cuba [GOC] has agreed for appointment of the PMC in the project. Accordingly, the tendering process for EPC contract would commence once the PMC in the project has been apppointed.
395 | 154 | 3 | GOILOC-266(P-1) | GOILOC-266 | Construction of water supply schemes in 25 towns of Tanzania and water supply project in Zanzibar Urban | PQ process completed - Contract yet to be awarded |  | G-266 | Tanzania | 500 | Prequalification of Consultant for I) Preparation of Detailed Project Report (DPR) and II) Project Management Consultant (PMC) for water supply project in Zanzibar Urban | 7.5 | DPR+PMC | 2018-08-17 | 2018-09-28 |  | - | - | Pre-qualified Companies List: 1) Feedback Infra Pvt. Ltd (Package 1) 2) Tata Consulting Engineers (Package 1 and 2) 3) Venkateshwara Enterprises (Package 1) 4) Wapcos Ltd. (Package 1 and 2) Contract Award: Draft tender for Zanzibar urban was reviewed by Exim Bank on 28.01.2019. Zanzibar Water Authority has also now issued Tender documents to the pre-qualified consultants on May 28, 2019 with last date of bid submission being July 11,2019. Bid evaluation report was received on October 04, 2019. Exim bank conveyed its no-objection on the bid evaluation report for DPR on October 10, 2019 and requested ZAWA to forward the Combined Technical and Financial evaluation report for DPR for our review. Combined technical and financial evaluation report and draft contract awarded to Tata Consulting Engineers were recived on December 10, 2019. The same have been reviwed by Exim Bank and conveyed to ZAWA on January23, 2020. Signed contract awarded to Tata Consulting Engineers for inclusion under the LOC is yet to be received.
395 | 154 | 3 | GOILOC-266(P-1) | GOILOC-266 | Construction of water supply schemes in 25 towns of Tanzania and water supply project in Zanzibar Urban | PQ document under preparation |  | G-266 | Tanzania | 500 | Construction of Water supply schemes in various towns of Tanzania | 460 | EPC |  |  |  | NA | NA | PQ Under Preparation. Terms of reference received from GO-TZA on February 24, 2020. Draft PQ document shall be shared with MoWI, GO-TZA by March 06, 2020.
401 | 160 | 4 | GOILOC-274(P-1) | GOILOC-274 | Infrastructure Development for Power Evacuation Facilities of Rooppur Nuclear Power Plant | PQ document under preparation |  | G-274 | Bangladesh | 4500 | Design, supply, delivery, installation, testing & commissioning of 400 kV bay extension at Kaliakoir, Aminbazar, Gopalganj and 230 kV bay extension at Baghabari and Dhamrai in Bangladesh | 14.96 | EPC |  |  |  | NA | NA | PQ committee's comments have been forwarded to PGCB for their concurrence. PQ to be launched shortly
401 | 160 | 4 | GOILOC-274(P-1) | GOILOC-274 | Infrastructure Development for Power Evacuation Facilities of Rooppur Nuclear Power Plant | PQ document under preparation |  | G-274 | Bangladesh | 4500 | Design, Supply, Installation, Testing & Commissioning of Rooppur-Dhaka 400kV Double Circuit Transmission Line on Trunkey Basis (Package-2) (Approx. 147.0km excluding 13 km River crossing line) | 134.12 | EPC |  |  |  | NA | NA | PQ committee's comments have been forwarded to PGCB for their concurrence. PQ to be launched shortly
401 | 160 | 4 | GOILOC-274(P-1) | GOILOC-274 | Infrastructure Development for Power Evacuation Facilities of Rooppur Nuclear Power Plant | PQ document under preparation |  | G-274 | Bangladesh | 4500 | Design, Supply, Installation, Testing & Commissioning of Aminbazar-Kaliakair 400kV Double Circuit Transmission Lines on Turnkey Basis. | 46.53 | EPC |  |  |  | NA | NA | PQ committee's comments have been forwarded to PGCB for their concurrence. PQ to be launched shortly
406 | 165 | 2 | GOILOC-278(P-1) | GOILOC-278 | Construction and upgradation of Base-Butaro-Kidaho Road Project | PQ to be Reinvited/Cancelled |  | G-278 | Rwanda | 66.6 | Construction and upgradation of Base-Butaro-Kidaho Road Project | 66.6 | EPC | 2018-07-13 | 2018-08-13 |  | NA | NA | Pre-Qualified Companies List: i) Afcons Infrastructure Ltd., ii) JMC Projects (India) ltd., iii) Ashoka Buildcon Ltd., iv) Ircon International Ltd. and v) APCO Infratech Pvt. Ltd. Contract Award: Only one bid from Afcons Infrastructure Ltd received, which is very high at USD 135.43 mn. GO-RWA has cancelled the tendering process and will re-bid among the prequalified companies. On May 31, 2019, GOR was advised to revalidate the cost estimates on basis of current prices and considering the 65% Indian content requirement prior to the re-bidding. GO-RWA has revalidated the project cost as USD 73.80 mn and requested for re-bidding among all empaneled Indian Companies in road sector with Exim Bank and Waiving 65% Indian content requirement rebidding. On August 05, 2019, GO-RWA was advised to re-bid among the prequalified companies and no further relaxation of Indian content requirement is feasible.
412 | 171 | 4 | GOILOC-284(P-1) | GOILOC-284 |  | PQ document under preparation |  | G-284 (LOC to EBID) | Benin | 500 | Rural Electrification of 100 communities in Benin | 37.7 | EPC |  |  |  | NA | NA | PQ Under Preparation. It will be uploaded post approval of PQ committee
412 | 171 | 4 | GOILOC-284(P-1) | GOILOC-284 |  | PQ document under preparation |  | G-284 (LOC to EBID) | Liberia | 500 | Barclayville -sasstown-Klowein road construction project in Liberia | 50 | PMC |  |  |  | NA | NA | PQ Under Preparation. It will be uploaded post approval of PQ committee
412 | 171 | 4 | GOILOC-284(P-1) | GOILOC-284 |  | PQ uploaded presently on website |  | G-284 (LOC to EBID) | Cote'd'Ivoire | 500 | Equipment and Rehabilitation Health facilities project in the Republic of Cote'd'Ivoire | 20 | EPC | 2020-02-07 | 2020-03-11 |  | NA | NA | NA
437 | 196 | 3 | GOILOC-309(P-1) | GOILOC-309 |  | PQ document under preparation |  | G-309 | Maldives | 800 | Expansion of Maldives Industrial Fisheries Company [MIFCO] Facilities in Maldives | 13.25 | DPR+PMC |  |  |  | NA | NA | 1. Draft PQ document forwarded to Govt. of Maldives on 09.08.2019 for review and additional information. 2. Response awaited from Govt. of Maldives. Reminder sent on September 16, 2019. 3. GOM on October 16, 2019 sent its comments/observations on the Draft PQ Document. Exim Bank on October 17, 2019 requested additional information from GOM on the harbour component under the project. Additional Information was shared by Govt. of Maldives on October 24, 2019 and October 28, 2019. 4. Exim Bank on October 29, 2019 proposed a consultancy structure for the pre-qualification of consultants under the project, as it is comprised of three varied components viz. (a) Supply of Carrier/ Collector Vessels (b) EPC works for Cold Storage Units at the Islands (c) Renovation including Expansion at Kanduoigiri of Harbour. 5. Further clarifications upon request were provided to GOM on October 31, 2019 by Exim Bank. 6. Reminder was sent on November 19, 2019 to GOM to confirm upon structure. 7. Ministry of Economic Development, GOM on November 20, 2019 informed Exim Bank that they are awaiting clearance from Ministry of Finance (MOF), GOM to confirm on structure, and will confirm to Bank as soon as a go-ahead is received from MOF, GOM.
437 | 196 | 3 | GOILOC-309(P-1) | GOILOC-309 |  | PQ process completed - Contract awarded |  | G-309 | Maldives | 800 | Water supply and sewerage system project in 34 Islands in Maldives | 3.6 | DPR+PMC | 2019-07-01 | 2019-07-30 | 2019-11-14 | 2019-12-23 | 2019-12-31 | Pre-Qualified Companies List: i) WAPCOS ltd. ii) Tata Consulting Engineers Ltd. iii) Shah Technical Consultants Ltd. iv) Venkateshwara Enterprises Contract Award: Contract awarded to Shah Technical included under LOC on 31.12.19.
167 | 471 | 2 | GOILOC-119(P-1) | GOILOC-119 |  | PQ process completed - Contract yet to be awarded |  | G-119 | Mongolia | 1000 | Oil Refinery project | 79.91 | EPC | 2019-07-29 | 2019-09-16 |  | NA | NA | Five applications received for which the evaluation has been completed . The prequalified companies are: [i] KEC International [ii] JMC Projects [iii] Afcons Infrastructure Ltd. [iv] Ashoka Buildcon Ltd. [v] Megha Engineering Infrastructure Ltd. Bidding document has been isued to the pre-qualified companies. The last date of bid submission was Feb 17,2020. Three companies out of five prequalified companies have submitted their bids. Bid evaluation is underway.
293 | 597 | 2 | GOILOC-187(P-1) | GOILOC-187 |  | PQ to be Reinvited/Cancelled |  | G-187 | Senegal | 41.96 | Setting up a Modern Abattoir, Meat Processing, Cold Storage, Rendering and Tannery Plant and Market Place in Senegal | 39.42 | EPC |  |  |  | NA | NA | 1) PQ document for EPC contractor has been prepared based on the DPR submitted by GK Sen [PMC and forwarded to Govt of Senegal on 01.03.2018 and 09.04.2018. 2) DPR Submitted to GOI on March 22, 2018. 3) PQ to be uploaded upon approval of DPR by GOI. Project on hold. MEA's advice awaited.
306 | 610 | 3 | GOILOC-201(P-3) | GOILOC-201 | [i] Modern Irrigated Agricultural Project; and [ii] Modern Irrigated Agricultural | PQ to be Reinvited/Cancelled |  | G-201 | Rwanda | 120.05 | [i] Export Targeted Modern Irrigated Agricultural Project (USD 60.22 million); and [ii] Extension of Export Targeted Modern Irrigated Agricultural Project (USD 59.83 million) : Mahama Lot 1 Project | 26.62 | EPC | 2016-11-11 | 2016-12-27 | 2018-10-22 | 2018-11-28 | NA | Pre-Qualified cos. List: i) JV of Technofab Engineering & KBL ii) Jain Irrigation Systems Ltd. Contract Award: Contract awarded to Jain Irrigation Systems Ltd. (JISL). Contract is yet to be included under LOC pending approval of GOI for relaxation in Indian content requirement to 65%. GOI's approval for Indian content relexatation received on November 11, 2019. JISL account has been classified as NPA by the bankers of JISL. Exim Bank on Nov 11, 2019 sought MEA's guidance to convey to GO-RWA about the ineligibility of JISL and to undertake fresh pre-qualification process for the captioned project. JISL’s account has been categorized as Non-Performing Asset (NPA) by its bankers hence it stands ineligible under the pre-qualification criteria as on date. On December 27, 2019, GO-RWA is advised to undertake fresh pre-qualification process for the project.
306 | 610 | 3 | GOILOC-201(P-3) | GOILOC-201 | [i] Modern Irrigated Agricultural Project; and [ii] Modern Irrigated Agricultural | PQ to be Reinvited/Cancelled |  | G-201 | Rwanda | 120.05 | [i] Export Targeted Modern Irrigated Agricultural Project (USD 60.22 million); and [ii] Extension of Export Targeted Modern Irrigated Agricultural Project (USD 59.83 million) : Mahama Lot II Project | 26.44 | EPC | 2017-11-21 | 2018-01-03 |  | NA | NA | Pre-Qualified Companies List: i) Jain Irrigation Systems Ltd. ii) Megha Engineering and Infrastructure Ltd. Contract Award: Yet to be awarded. Bid evaluation is under way. Megha Engineering filed complaint with Rwanda Public Procurement Authority (RPPA) against their technical disqualification, which has been declined by RPPA. Financial bid of Jain Irrigation was opened on December 05, 2018. Financial bid and draft contract agreement received from RAB on March 14, 2019. Exim Bank on April 29, 2019 has requested RAB to reconsider the technical evaluation of MEIL. RAB on June 12, 2019 declined to review the technical bid evaluation report and requested concurrence to award the contract to JISL. JISL’s account has been categorized as Non-Performing Asset (NPA) by its bankers hence it stands ineligible under the pre-qualification criteria as on date. On December 27, 2019, GO-RWA is advised to undertake fresh pre-qualification process for the project. RAB on January 15, 2020 agreed for fresh prequalification for the project, however comments are awaited on the PQ doscument for fresh prequalification.
349 | 653 | 2 | GOILOC-233(P-1) | GOILOC-233 | Power Distribution Project in Bandundu Province of D R Congo | PQ process completed - Contract awarded |  | G-233 | D.R.Congo | 34.5 | Development of Power Distribution Project in Bandundu Province of D. R. Congo | 2.95 | PMC | 2017-01-09 | 2017-02-08 | 2017-11-07 |  | 2017-12-22 | Pre-Qualified Cos. List: i) Tata Consulting Engineers ii) WAPCOS Ltd. Contract award: WAPCOS Ltd. on 07.11.2017
360 | 664 | 2 | GOILOC-244(P-1) | GOILOC-244 | Tranmission Line and Sub-station | PQ uploaded presently on website |  | G-244 | Nicaragua | 31.29 | Transmission Line & Substation Project | 24 | PMC | 2020-02-14 | 2020-03-16 |  | NA | NA | NA
333 | 637 | 1 | GOILOC-227(P-1) | GOILOC-227 | Upgrading/ improvement of roads viz. Charikot-Tamakoshi-Jiri sector of Lamosanghu-Tamakoshi-Jiri Road | PQ to be Reinvited/Cancelled |  | G-227 | Nepal | 550 | Various road projects | 49.82 | CC | 2017-09-18 | 2017-12-14 |  |  |  | Pre-Qualfied Companies List: [i] Package III- Supreme-Swachchanda JV; ECI Engineering & Constructions; IL & FS Transportation Ltd; JMC Projects Ltd. Pre-Qualfied Companies List (after re-invitation in January 2019) : [i] Package III- Ashoka Buildcon Ltd., Telecommunication Consultants India Ltd., Woodhill-Lama JV. No Bid was received under Package III. DOR to re-invite PQ. DOR has requested for single stage two envelope for contracts where no bids were received. The matter was refered to MEA-DPA on November 9, 2018. MEA on 07.01.2019 advised to reinvite applications from the prequalified companies. Application document for reinvitation published on 25.01.2019. 14 Applications were received and were jointly evaluated on April 24-25, 2019 by Exim Bank and DOR-GON. Four Applicants were prequalified. MBL Infrastructure Ltd. has been excluded from list of pre-qualified companies due to its NPA status. GON has been informed that Woodhill-Lama JV was debarred by Government owned company viz. NHIDCL and hence be excluded from list of pre-qualified applicants. Tender document has been published by DOR on 20.02.2020.

## Sheet3
SerialNo | ProjectID | More | ProjectCode | LOC NUMBER | Purpose | Category | Sr. no. | LOC Ref. No. | Country | LOC amount (USD million) | Project | Project Cost for which PQ is being /was undertaken (USD mn) | Category | PQ documents published on | Last date for submission | Date of Contract Signing | Date of receipt of Contract Agreement & Contract Inclusion Form by Exim Bank | Date of Contract Inclusion by Exim Bank | Status
358 | 662 | 5 | GOILOC-242(P-1) | GOILOC-242 | Supply of 160 passenger coaches to Sri Lanka Railways | PQ process completed, contract awarded |  | G-242 | Sri Lanka | 318 | Supply of 160 Passenger Coaches | 58 | SPPLY | 42933 | 42979 | 43350 | 43389 | 43399 | Pre-Qualified Companies List: i) RITES Ltd Contract Award: Contract awarded to RITES. Contract has been included under the LOC on October 26, 2018.
358 | 662 | 5 | GOILOC-242(P-1) | GOILOC-242 |  | PQ process completed - Contract Yet to be awarded |  | G-242 | Sri Lanka | 318 | Signalling Project between Maho and Anuradhapura | 12.6 | EPC | 43472 | 43514 | NA | NA | NA | Pre-Qualified Companies List: i) IRCON Intl. Ltd. ii) KEC International Ltd in JV with TVM Signalling and Transportation Systems Pvt Ltd. (KEC – TSTS JV) iii) Kiran Infra Engineers Ltd. iv) Texmaco Rail & Engineering Ltd. Contract Award: Yet to be awarded. Draft of tender document received from GOSL on August 7, 2019 was reviewed and comments sent to GOSL on September 4, 2019. Thereafter, revised Draft tender document was received from GOSL on September 30, 2019, Exim Bank on October 7, 2019 has shared its comments to GOSL. Exim Bank on November 22, 2019 has again provided its comments on the revised Draft tender document shared by GOSL and given go-ahead to GOSL for initiaing the tendering process.
358 | 662 | 5 | GOILOC-242(P-1) | GOILOC-242 |  | PQ process completed - Contract Yet to be awarded |  | G-242 | Sri Lanka | 318 | Ratmalana Railway Workshop Project | 6 | PMC | 43434 | 43494 | NA | NA | NA | 1. A total of 6 Applications were received by Exim Bank and the evaluation of the same has been completed. 2. Exim Bank has shared with GOSL the names of two qualified indian companies and shared its comments on the Draft Tender document received from GOSL on August 26, 2019. GOSL on Sepetmber 23, 2019 has again sent its comments of the tender document. Exim Bank has submitted comments to GOSL on October 3, 2019 and advised to initiate the tendering process. GOSL has initiated the tendering process and the last date for submission of the tender application is February 20, 2020. Exim Bank on February 28,2020 has advised GOSL to provide the current status of tendering process and share the Draft technical bid evalution report, in case the same has been completed. Prequalified companies list: i) RITES Ltd. ii) PEMS Engineering Consultants Pvt. Ltd.
358 | 662 | 5 | GOILOC-242(P-1) | GOILOC-242 |  | PQ process completed, contract awarded |  | G-242 | Sri Lanka | 318 | Upgradation of Railway Line from Maho to Omanthai [129 Km] | 136.3 | EPC | 42933 | 42979 | 43664 | 43725 | 43784 | Pre-Qualified Companies List: i) IRCON Intl. Ltd. ii) L&T Ltd. iii) Texmaco Rail & Engg. Ltd. Contract Award: IRCON Intl Ltd has been shortlisted and the contract has been signed on 18.07.2019. Contract has been included under the LOC on 15.11.2019 .
358 | 662 | 5 | GOILOC-242(P-1) | GOILOC-242 |  | PQ document under preparation |  | G-242 | Sri Lanka | 382.37 | Supply of 500 buses | 15.03 | SPPLY | Yet to be Published | NA | NA | NA | NA | 1) Exim Bank has prepared the pre-qualification documents for supply of 500 buses to SLTB, based on the specifications received from GOSL. 2) The Pre-qualification document was sent to GOSL for its concurrence on February 05, 2019. Reminder sent on May 14, 2019, July 4, 2019, July 10, 2019 and October 24, 2019. 3) Exim Bank has shared the revised PQ document on December 06, 2019. GOSL on December 10, 2019 has informed that the approval for the project is pending with Sri Lankan Cabinet.

## Sheet2
SerialNo | ProjectID
362 | 121
363 | 122
364 | 123
365 | 124
366 | 125
367 | 126
368 | 127
369 | 128
370 | 129
371 | 130
372 | 131
373 | 132
374 | 133
375 | 134
376 | 135
377 | 136
378 | 137
379 | 138
380 | 139
381 | 140
382 | 141
383 | 142
384 | 143
385 | 144
386 | 145
387 | 146
388 | 147
389 | 148
390 | 149
391 | 150
392 | 151
393 | 152
394 | 153
395 | 154
154
396 | 155
397 | 156
398 | 157
399 | 158
400 | 159
401 | 160
402 | 161
403 | 162
404 | 163
405 | 164
406 | 165
407 | 166
408 | 167
409 | 168
410 | 169
411 | 170
412 | 171
413 | 172
414 | 173
415 | 174
416 | 175
417 | 176
418 | 177
419 | 178
420 | 179
421 | 180
422 | 181
423 | 182
424 | 183
425 | 184
426 | 185
427 | 186
428 | 187
429 | 188
430 | 189
431 | 190
432 | 191
433 | 192
434 | 193
435 | 194
436 | 195
437 | 196
438 | 197
439 | 198
440 | 199
441 | 200
442 | 201
443 | 202
444 | 203
445 | 204
446 | 205
447 | 206
448 | 207
449 | 208
450 | 209
451 | 210
452 | 211
453 | 212
454 | 213
455 | 214
456 | 215
457 | 216
458 | 217
459 | 218
460 | 219
461 | 220
462 | 221
463 | 222
464 | 223
465 | 224
466 | 225
467 | 226
468 | 227
469 | 228
470 | 229
471 | 230
472 | 231
473 | 232
474 | 233
475 | 234
476 | 235
477 | 236
478 | 237
479 | 238
480 | 239
481 | 240
482 | 241
483 | 242
484 | 243
485 | 244
486 | 245
487 | 246
488 | 247
489 | 248
490 | 249
491 | 250
492 | 251
493 | 252
494 | 253
495 | 254
496 | 255
497 | 256
498 | 257
499 | 258
500 | 259
501 | 260
502 | 261
503 | 262
504 | 263
505 | 264
506 | 265
507 | 266
508 | 267
509 | 268
510 | 269
511 | 270
512 | 271
513 | 272
514 | 273
515 | 274
516 | 275
517 | 276
518 | 277
519 | 278
520 | 279
521 | 280
522 | 281
523 | 282
524 | 283
525 | 284
526 | 285
527 | 286
528 | 287
529 | 288
530 | 289
531 | 290
532 | 291
533 | 292
534 | 293
535 | 294
536 | 295
537 | 296
538 | 297
539 | 298
540 | 299
541 | 300
542 | 301
543 | 302
544 | 303
545 | 304
1 | 305
2 | 306
3 | 307
4 | 308
5 | 309
6 | 310
7 | 311
8 | 312
9 | 313
10 | 314
11 | 315
12 | 316
13 | 317
14 | 318
15 | 319
16 | 320
17 | 321
18 | 322
19 | 323
20 | 324
21 | 325
22 | 326
23 | 327
24 | 328
25 | 329
26 | 330
27 | 331
28 | 332
29 | 333
30 | 334
31 | 335
32 | 336
33 | 337
34 | 338
35 | 339
36 | 340
37 | 341
38 | 342
39 | 343
40 | 344
41 | 345
42 | 346
43 | 347
44 | 348
45 | 349
46 | 350
47 | 351
48 | 352
49 | 353
50 | 354
51 | 355
52 | 356
53 | 357
54 | 358
55 | 359
56 | 360
57 | 361
58 | 362
59 | 363
60 | 364
61 | 365
62 | 366
63 | 367
64 | 368
65 | 369
66 | 370
67 | 371
68 | 372
69 | 373
70 | 374
71 | 375
72 | 376
73 | 377
74 | 378
75 | 379
76 | 380
77 | 381
78 | 382
79 | 383
80 | 384
81 | 385
82 | 386
83 | 387
84 | 388
85 | 389
86 | 390
87 | 391
88 | 392
89 | 393
90 | 394
91 | 395
92 | 396
93 | 397
94 | 398
95 | 399
96 | 400
97 | 401
98 | 402
99 | 403
100 | 404
101 | 405
102 | 406
103 | 407
104 | 408
105 | 409
106 | 410
107 | 411
108 | 412
109 | 413
110 | 414
111 | 415
112 | 416
113 | 417
114 | 418
115 | 419
116 | 420
117 | 421
118 | 422
119 | 423
120 | 424
121 | 425
122 | 426
123 | 427
124 | 428
125 | 429
126 | 430
127 | 431
128 | 432
129 | 433
130 | 434
131 | 435
132 | 436
133 | 437
134 | 438
135 | 439
136 | 440
137 | 441
138 | 442
139 | 443
140 | 444
141 | 445
142 | 446
143 | 447
144 | 448
145 | 449
146 | 450
147 | 451
148 | 452
149 | 453
150 | 454
151 | 455
152 | 456
153 | 457
154 | 458
155 | 459
156 | 460
157 | 461
158 | 462
159 | 463
160 | 464
161 | 465
162 | 466
163 | 467
164 | 468
165 | 469
166 | 470
167 | 471
168 | 472
169 | 473
170 | 474
171 | 475
172 | 476
173 | 477
174 | 478
175 | 479
176 | 480
177 | 481
178 | 482
179 | 483
180 | 484
181 | 485
182 | 486
183 | 487
184 | 488
185 | 489
186 | 490
187 | 491
188 | 492
189 | 493
190 | 494
191 | 495
192 | 496
193 | 497
194 | 498
195 | 499
196 | 500
197 | 501
198 | 502
199 | 503
200 | 504
201 | 505
202 | 506
203 | 507
204 | 508
205 | 509
206 | 510
207 | 511
208 | 512
209 | 513
210 | 514
211 | 515
212 | 516
213 | 517
214 | 518
215 | 519
216 | 520
217 | 521
218 | 522
219 | 523
220 | 524
221 | 525
222 | 526
223 | 527
224 | 528
225 | 529
226 | 530
227 | 531
228 | 532
229 | 533
230 | 534
231 | 535
232 | 536
233 | 537
234 | 538
235 | 539
236 | 540
237 | 541
238 | 542
239 | 543
240 | 544
241 | 545
242 | 546
243 | 547
244 | 548
245 | 549
246 | 550
247 | 551
248 | 552
249 | 553
250 | 554
251 | 555
252 | 556
253 | 557
254 | 558
255 | 559
256 | 560
257 | 561
258 | 562
259 | 563
260 | 564
261 | 565
262 | 566
263 | 567
264 | 568
265 | 569
266 | 570
267 | 571
268 | 572
269 | 573
270 | 574
271 | 575
272 | 576
273 | 577
274 | 578
275 | 579
276 | 580
277 | 581
278 | 582
279 | 583
280 | 584
281 | 585
282 | 586
283 | 587
284 | 588
285 | 589
286 | 590
287 | 591
288 | 592
289 | 593
290 | 594
291 | 595
292 | 596
293 | 597
294 | 598
295 | 599
296 | 600
297 | 601
298 | 602
299 | 603
300 | 604
301 | 605
302 | 606
303 | 607
304 | 608
305 | 609
306 | 610
307 | 611
308 | 612
309 | 613
310 | 614
311 | 615
312 | 616
313 | 617
314 | 618
315 | 619
316 | 620
317 | 621
318 | 622
319 | 623
320 | 624
321 | 625
322 | 626
323 | 627
324 | 628
325 | 629
326 | 630
327 | 631
328 | 632
329 | 633
330 | 634
331 | 635
332 | 636
333 | 637
334 | 638
335 | 639
336 | 640
337 | 641
338 | 642
339 | 643
340 | 644
341 | 645
342 | 646
343 | 647
344 | 648
345 | 649
346 | 650
347 | 651
348 | 652
349 | 653
350 | 654
351 | 655
352 | 656
353 | 657
354 | 658
355 | 659
356 | 660
357 | 661
358 | 662
359 | 663
360 | 664
361 | 665